	95
Section VIII.  Security Forms 	106	
Section VIII.  Security Forms	101
[image: Logo of Ghana Crest]
GOVERNMENT OF GHANA
ELLEMBELLE DISTRICT ASSEMBLY


                                     PROCUREMENT OF WORKS

NATIONAL COMPETITIVE TENDER
TENDER DOCUMENT


CONSTRUCTION OF 1 NO. MATERNITY BLOCK AND 1NO.LABORATORY AND RADIOLOGY BLOCK AT NKROFUL
(PACKAGE NO.: WR/EDA/WKS/2026/009)


CLIENT
ELLEMBLLE DISTRICT ASSEMBLY
P. O. BOX 34
NKROFUL
CONSULTANT
WORKS DEPARTMENT
ELLEMBELLE DISTRICT ASSEMBLY
NKROFUL



                                                                     


NOVEMBER, 2026


Table of Contents

Invitation to TenderError! Bookmark not defined.
Section I.   Instructions to Tenderer	5
Table of Clauses	6
Instructions to Tenderer	7
Section II.  Forms of Tender, Qualification Information, Letter of Acceptance, and Agreement	28
Contractor’s Tender	29
ATTACHMENTS TO THE TENDER	31
Attach. 1	Power of Attorney	31
Attach. 2	Tender Security	31
Attach. 3	Price Schedules	31
Attach. 4	Documentary Evidence of Tenderer’s Qualifications	31
Attach. 5	Others:	31
-	Work Programme and Schedule	31
-	List of Subcontractors	31
-	Design Drawings, Calculations and Technical Alternatives	31
Qualification Information	32
Qualification Information	32
Section III.  Conditions of Contract	37
Table of Clauses	38
Section IV.  Contract Data	62
Section V.  Specifications	67
Section VI.  Drawings	92
Section VII.  Bill of Quantities	94
Section VIII.  Security Forms	95
Annex A Form:  Tender Security (Bank Guarantee)	96
Annex B Form (Alternative 2):  Performance Bond	99
Annex C Form:  Bank Guarantee for Advance Payment	101





INVITATION TO TENDER (ITT)











INVITATION TO TENDER (ITT)

	Contract Name

	
	CONSTRUCTION OF 1 NO.MERTANITY BLOCK AND 1NO.LABORATORY AND RADIOLOGY BLOCK AT NKROFUL



	Tender Issuance Date

	
	[bookmark: _GoBack]  21  ST OCTOBER,2026



	Contract Number

	
	WR/EDA/WKS/2026/009



	
1. THE ELLEMBELLE DISTRICT ASSEMBLY intends to apply part of it DACF-RFG allocations to cover eligible payments under the contract for the construction of the above-named project

2. Tender is open to all eligible Contractors/Tenderers from eligible source countries as defined in the Guidelines of the Public Procurement Board of the Republic of Ghana.

3. Completed and sealed Tender must be accompanied with a bid security of 2.5% of tender price in addition to the following document
· Tax Clearance Certificate
· Labour Certificate
· SSNIT Clearance Certificate
· Certificate of Incorporation
· Certificate to commence business
· Ministry of Works and Housing
· Valid Procurement Authority Registration Certificate
· Evidence of past Work Experience
4. Tenders shall be delivered on or before 10TH NOVEMBER, 2026 at 10:00 hours GMT to the address below    
                                       THE DISTRICT CHIEF EXECUTIVE
ELLEMBELLE DISTRICT ASSEMBLY
P.O. BOX 34
NKROFUL
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[bookmark: _Toc343309614][bookmark: _Toc55111304]
Table of Clauses
A.  General	7
1.	Scope of Tender	7
2.	Source of Funds	7
3.	Eligible Tenderers	7
4.	Qualification of the Tenderer	8
5.	One Tender per Tenderer	10
6.	Cost of Tender	10
7.	Site Visit	11
B.  Tender Documents	11
8.	Content of Tender Documents	11
9.	Clarification of Tender Documents	11
10.	Amendment of Tender Documents	11
C.  Preparation of Tenders	12
11.	Language of Tender	12
12.	Documents Comprising the Tender	12
13.	Tender Prices	12
14.	Currencies of Tender and Payment	12
15.	Tender Validity	13
16.	Tender Security	14
17.	Alternative Proposals by Tenderers	14
18.	Format and Signing of Tender	15
D.  Submission of Tenders	16
19.	Sealing and Marking of Tenders	16
20.	Deadline for Sub-mission of Tenders	16
21.	Late Tenders	16
22.	Modification and Withdrawal of Tenders	16
E.  Tender Opening and Evaluation	17
23.	Tender Opening	17
24.	Process to Be Confidential	17
25.	Clarification of Tenders	17
26.	Examination of Tenders and Determination of Responsiveness	18
27.	Correction of Errors	18
28.	Currency for Tender Evaluation	19
29.	Evaluation and Comparison of Tenders	19
30.	Preference for Domestic Tenderers	20
F.  Award of Contract	21
31.	Award Criteria	21
32.	Employer’s Right to Accept any Tender and to Reject any or all Tenders	21
33.	Notification of Award and Signing of Agreement	21
34.	Performance Security	22
35.	Advance Payment and Security	22
36.	Adjudicator	22
G.  Tender Data	25
[bookmark: _Instructions_to_Tenderers]
Instructions to Tenderers

[bookmark: _Toc343309763][bookmark: _Toc55112508]A.  General

	[bookmark: _Toc343309764][bookmark: _Toc55112509]1.	Scope of Tender
	1.1	The Employer as defined in the Contract Data, invites Tenders for the construction of Works, as described in the Contract Data.  The name and identification number of the Contract is provided in the Contract Data.

1.2	The successful Tenderer will be expected to complete the Works by the Intended Completion Date specified in the Contract Data.


	[bookmark: _Toc343309765][bookmark: _Toc55112510]2.	Source of Funds
	2.1    The Procurement Entity (hereinafter called “Employer”) named in the Tender Data Sheet shall fund this procurement from part of its budgetary allocation toward the realization of the project named in the TDS. 
2.2    Payments will be made only at the request of the Employer and upon approval by a designated official of the Republic of Ghana in accordance with the terms and conditions of the contract between the Purchaser and the Supplier (hereinafter called the Contract), and will be subject in all respects to the Financial Administration Act, 2003 (Act 654) the Republic of Ghana. No party other than the Supplier shall derive any rights from the Contract or have any claim to the funds.

	[bookmark: _Toc343309766]
[bookmark: _Toc55112511]3.	Eligible Tenderers
	
3.1	This request for quotation is exclusive as defined in the Procurement Guidelines of the Procurement Board of the Republic of Ghana.  Any materials, equipment, and services to be used in the performance of the Contract shall have their origin in eligible source countries.

3.2	All Tenderers shall provide in Section 2, Forms of Tender and Qualification Information, a statement that the Tenderer (including all members of a joint venture and subcontractors) is not associated, nor has been associated in the past, directly or indirectly, with the consultant or any other entity that has prepared the design, specifications, and other documents for the Project or being proposed as Project Manager for the Contract.  A firm that has been engaged by the Employer to provide consulting services for the preparation or supervision of the Works, and any of its affiliates, shall not be eligible to Tender.

3.3	Government-owned enterprises in the country may only participate if they are legally and financially autonomous, and operate under commercial law.

	[bookmark: _Toc343309767][bookmark: _Toc55112512]4.	Qualification of the Tenderer
	4.1	All Tenderers shall provide in Section 2, Forms of Tender and Qualification Information, a preliminary description of the proposed work method and schedule, including drawings and charts, as necessary.

4.2	In the event that prequalification of potential Tenderers has been undertaken, only Tenders from prequalified Tenderers will be considered for award of Contract.  These qualified Tenderers should submit with their Tenders any information updating their original prequalification applications or, alternatively, confirm in their Tenders that the originally-submitted prequalification information remains essentially correct as of the date of Tender submission.  The update or confirmation should be provided in Section 2.

4.3	If the Employer has not undertaken prequalification of potential Tenderers, all Tenderers shall include the following information and documents with their Tenders in Section 2, unless otherwise stated in the Tender Data:

(a)	copies of original documents defining the constitution or legal status, place of registration, and principal place of business; written power of attorney of the signatory of the Tender to commit the Tenderer;

(b)	total monetary value of construction work performed for each of the last five years;

(c)	experience in works of a similar nature and size for each of the last five years, and details of work under way or contractually committed; and clients who may be contacted for further information on those contracts;

(d)	major items of construction equipment proposed to carry out the Contract;

(e)	qualifications and experience of key site management and technical personnel proposed for the Contract;

(f)	reports on the financial standing of the Tenderer, such as profit and loss statements and auditor’s reports for the past five years;

(g)	evidence of adequacy of working capital for this Contract (access to line(s) of credit and availability of other financial resources);

(h)	authority to seek references from the Tenderer’s bankers;

(i)	information regarding any litigation, current or during the last five years, in which the Tenderer is involved, the parties concerned, and disputed amount; and

(j)	proposals for subcontracting components of the Works amounting to more than 10 percent of the Contract Price.

4.4	Tenders submitted by a joint venture of two or more firms as partners shall comply with the following requirements, unless otherwise stated in the Tender Data:

(a)	the Tender shall include all the information listed in Sub-Clause 4.3 above for each joint venture partner;

(b)	the Tender shall be signed so as to be legally binding on all partners;

(c)	all partners shall be jointly and severally liable for the execution of the Contract in accordance with the Contract terms;

(d)	one of the partners will be nominated as being in charge, authorized to incur liabilities, and receive instructions for and on behalf of any and all partners of the joint venture; and

(e)	the execution of the entire Contract, including payment, shall be done exclusively with the partner in charge.

4.5	To qualify for award of the Contract, Tenderers shall meet the following minimum qualifying criteria:

(a)	annual volume of construction work of at least the amount specified in the Tender Data;

(b)	experience as prime contractor in the construction of at least two works of a nature and complexity equivalent to the Works over the last 10 years (to comply with this requirement, works cited should be at least 70 percent complete);

(c)	proposals for the timely acquisition (own, lease, hire, etc.) of the essential equipment listed in the Tender Data;

(d)	a Contract Manager with five years’ experience in works of an equivalent nature and volume, including no less than three years as Manager; and

(e)	liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than the amount specified in the Tender Data.

A consistent history of ligitigation or arbitration awards against the Applicant or any partner of a Joint Venture may result in disqualification.

4.6	The figures for each of the partners of a joint venture shall be added together to determine the Tenderer’s compliance with the minimum qualifying criteria of Sub-Clause 4.5(a) and (e); however, for a joint venture to qualify, each of its partners must meet at least 25 percent of minimum criteria 4.5(a), (b), and (e) for an individual Tenderer, and the partner in charge at least 40 percent of those minimum criteria.  Failure to comply with this requirement will result in rejection of the joint venture’s Tender.  Subcontractors’ experience and resources will not be taken into account in determining the Tenderer’s compliance with the qualifying criteria, unless otherwise stated in the Tender Data.

4.7	Domestic Tenderers and joint ventures of domestic and foreign Tenderers applying for eligibility for a 7½-percent margin of preference in Tender evaluation shall supply all information to satisfy the criteria for eligibility as described in Clause 30 of these Instructions to Tenderers.


	[bookmark: _Toc343309768][bookmark: _Toc55112513]5.	One Tender per Tenderer
	5.1	Each Tenderer shall submit only one Tender, either individually or as a partner in a joint venture.  A Tenderer who submits or participates in more than one Tender (other than as a subcontractor or in cases of alternatives that have been permitted or requested) will cause all the proposals with the Tenderer’s participation to be disqualified.



	[bookmark: _Toc343309769][bookmark: _Toc55112514]6.	Cost of Tender
	6.1	The Tenderer shall bear all costs associated with the preparation and submission of his Tender, and the Employer will in no case be responsible or liable for those costs.


	[bookmark: _Toc343309770][bookmark: _Toc55112515]7.	Site Visit
	7.1	The Tenderer, at the Tenderer’s own responsibility and risk, is encouraged to visit and examine the Site of Works and its surroundings and obtain all information that may be necessary for preparing the Tender and entering into a contract for construction of the Works.  The costs of visiting the Site shall be at the Tenderer’s own expense.



[bookmark: _Toc343309771][bookmark: _Toc55112516]

B.  Tender Documents

	[bookmark: _Toc343309772][bookmark: _Toc55112517]8.	Content of Tender Documents
	8.1	The set of Tender documents comprises the documents listed in the table below and addenda issued in accordance with Clause 10:

Section	I	Instructions to Tenderers
II	Forms of Tender and Qualification Information
III	Conditions of Contract
IV	Tender Data
V	Specifications
VI	Drawings
VII	Bill of Quantities/Activity Schedule
VIII	Forms of Securities

8.2	Tenderers should complete and return sections II, IV and VII.


	[bookmark: _Toc343309773][bookmark: _Toc55112518]9.	Clarification of Tender Documents
	9.1	A prospective Tenderer requiring any clarification of the Tender documents may notify the Employer in writing or by cable (“cable” includes telex, facsimile and email) at the Employer’s address indicated in the invitation to Tender.  The Employer will respond to any request for clarification received earlier than 28 days prior to the deadline for submission of Tenders.  Copies of the Employer’s response will be forwarded to all purchasers of the Tender documents, including a description of the inquiry, but without identifying its source.


	[bookmark: _Toc343309774][bookmark: _Toc55112519]10.	Amendment of Tender Documents
	10.1	Before the deadline for submission of Tenders, the Employer may modify the Tender documents by issuing addenda.

10.2	Any addendum thus issued shall be part of the Tender documents and shall be communicated in writing or by cable to all purchasers of the Tender documents. Prospective Tenderers shall acknowledge receipt of each addendum by cable to the Employer.

10.3	To give prospective Tenderers reasonable time in which to take an addendum into account in preparing their Tenders, the Employer shall extend, as necessary, the deadline for submission of Tenders, in accordance with Sub-Clause 20.2 below.


[bookmark: _Toc343309775][bookmark: _Toc55112520]

C.  Preparation of Tenders

	[bookmark: _Toc343309776][bookmark: _Toc55112521]11.	Language of Tender
	11.1	All documents relating to the Tender shall be in the language specified in the Contract Data.


	[bookmark: _Toc343309777][bookmark: _Toc55112522]12.	Documents Comprising the Tender
	12.1	The Tender submitted by the Tenderer shall comprise the following:

(a)	The Tender (in the format indicated in Section 2);
(b)	Tender Security;
(c)	Priced Bill of Quantities;
(d)	Qualification Information Form and Documents;
(e)	Alternative offers where invited;

and any other materials required to be completed and submitted by Tenderers, as specified in the Tender Data.


	[bookmark: _Toc343309778][bookmark: _Toc55112523]13.	Tender Prices
	13.1	The Contract shall be for the whole Works, as described in Sub-Clause 1.1, based on the priced Bill of Quantities submitted by the Tenderer.

13.2	The Tenderer shall fill in rates and prices for all items of the Works described in the Bill of Quantities.  Items for which no rate or price is entered by the Tenderer will not be paid for by the Employer when executed and shall be deemed covered by the other rates and prices in the Bill of Quantities.

13.3	All duties, taxes, and other levies payable by the Contractor under the Contract, or for any other cause, as of the date 28 days prior to the deadline for submission of Tenders, shall be included in the rates, prices, and total Tender price submitted by the Tenderer.

13.4	The rates and prices quoted by the Tenderer shall be subject to adjustment during the performance of the Contract if provided for in the Tender and Contract Data and the provisions of Clause 47 of the Conditions of Contract.  The Tenderer shall submit with the Tender all the information required under the Contract Data and Clause 47 of the Conditions of Contract.


	[bookmark: _Toc343309779][bookmark: _Toc55112524]14.	Currencies of Tender and Payment
	14.1	The unit rates and prices shall be quoted by the Tenderer entirely in the currency of the Employer’s country as specified in the Contract Data.  Foreign currency requirements shall be indicated as a percentage of the Tender price (excluding provisional sums) and shall be payable at the option of the Tenderer in up to three foreign currencies of any eligible country. 

14.2	The rates of exchange to be used by the Tenderer in arriving at the local currency equivalent and the percentage(s) mentioned in para. 14.1 above shall be the selling rates for similar transactions established by the authority specified in the Contract Data prevailing on the date 28 days prior to the latest deadline for submission of Tenders.  These exchange rates shall apply for all payments so that no exchange risk will be borne by the Tenderer.  If the Tenderer uses other rates of exchange, the provisions of Clause 28.1 shall apply.  In any case, payments will be computed using the rates quoted in the Tender.

14.3	Tenderers shall indicate details of their expected foreign currency requirements in the Tender.

14.4	Tenderers may be required by the Employer to clarify their foreign currency requirements and to substantiate that the amounts included in the rates and prices and in the Contract Data are reasonable and responsive to Sub-Clause 14.1.


	[bookmark: _Toc343309780][bookmark: _Toc55112525]15.	Tender Validity
	15.1	Tenders shall remain valid for the period specified in the Tender Data.

15.2	In exceptional circumstances, the Employer may request that the Tenderers extend the period of validity for a specified additional period.  The request and the Tenderers’ responses shall be made in writing or by cable.  A Tenderer may refuse the request without forfeiting the Tender Security.  A Tenderer agreeing to the request will not be required or permitted to otherwise modify the Tender, but will be required to extend the validity of Tender Security for the period of the extension, and in compliance with Clause 16 in all respects.

15.3	In the case of contracts in which the Contract Price is fixed (not subject to price adjustment), if the period of Tender validity is extended beyond 60 days, the amounts payable in local and foreign currency to the Tenderer selected for award, shall be increased by applying to both the local and the foreign currency component of the payments, respectively, the factors specified in the Tender Data or in the request for extension, for the period of delay beyond 60 days after the expiry of the initial Tender validity, up to the notification of award.  Tender evaluation will be based on the Tender prices without taking the above correction into consideration.





	[bookmark: _Toc343309781][bookmark: _Toc55112526]16.	Tender Security
	16.1	The Tenderer shall furnish, as part of the Tender, a Tender Security in local currency or in a freely convertible currency, in the amount specified in the Tender Data.

16.2	The Tender Security shall, at the Tenderer’s option, be in the form of a certified check, bank draft, letter of credit, or a bank guarantee from a reputable bank located in the country of the Employer or abroad.  The format of the Tender Security should be in accordance with the form of Tender Security included in Section 8 or another form acceptable to the Employer.  Tender Security shall be valid for 28 days beyond the validity of the Tender.

16.3	Any Tender not accompanied by an acceptable Tender Security shall be rejected by the Employer.  The Tender Security of a joint venture must define as “Tenderer” all joint venture partners and list them in the following manner:  a joint venture consisting of “______,” “______,” and “______”.

16.4	The Tender Security of unsuccessful Tenderers will be returned within 28 days of the end of the Tender validity period specified in Sub-Clause 15.1.

16.5	The Tender Security of the successful Tenderer will be discharged when the Tenderer has signed the Agreement and furnished the required Performance Security.

16.6	The Tender Security may be forfeited

(a)	if the Tenderer withdraws the Tender after Tender opening during the period of Tender validity;

(b)	if the Tenderer does not accept the correction of the Tender price, pursuant to Clause 27; or

(c)	in the case of a successful Tenderer, if the Tenderer fails within the specified time limit to

(i)	sign the Agreement; or

(ii)	furnish the required Performance Security.


	[bookmark: _Toc343309782][bookmark: _Toc55112527]17.	Alternative Proposals by Tenderers
	17.1	Tenderers shall submit offers that comply with the requirements of the Tender documents, including the basic technical design as indicated in the drawings and specifications.  Alternatives will not be considered, unless specifically allowed in the Tender Data.  If so allowed, Sub-Clause 17.2 shall govern.

17.2	If so allowed in the Tender Data, Tenderers wishing to offer technical alternatives to the requirements of the Tender documents must also submit a Tender that complies with the requirements of the Tender documents, including the basic technical design as indicated in the drawings and specifications.  In addition to submitting the basic Tender, the Tenderer shall provide all information necessary for a complete evaluation of the alternative by the Employer, including design calculations, technical specifications, breakdown of prices, proposed construction methods and other relevant details.  Only the technical alternatives, if any, of the lowest evaluated Tenderer conforming to the basic technical requirements shall be considered by the Employer.


	[bookmark: _Toc343309783][bookmark: _Toc55112528]18.	Format and Signing of Tender
	18.1	The Tenderer shall prepare one original of the documents comprising the Tender as described in Clause 12 of these Instructions to Tenderers, bound with the volume containing the Form of Tender, and clearly marked “ORIGINAL.”  In addition, the Tenderer shall submit copies of the Tender, in the number specified in the Tender Data, and clearly marked as “COPIES.”  In the event of discrepancy between them, the original shall prevail.

18.2	The original the Tender shall be typed or written in indelible ink and shall be signed by a person or persons duly authorized to sign on behalf of the Tenderer, pursuant to Sub-Clauses 4.3(a) or 4.4(b), as the case may be.  All pages of the Tender where entries or amendments have been made shall be initialed by the person or persons signing the Tender.

18.3	The Tender shall contain no alterations or additions, except those to comply with instructions issued by the Employer, or as necessary to correct errors made by the Tenderer, in which case such corrections shall be initialed by the person or persons signing the Tender.


[bookmark: _Toc343309784][bookmark: _Toc55112529]

D.  Submission of Tenders

	[bookmark: _Toc343309785][bookmark: _Toc55112530]19.	Sealing and Marking of Tenders
	19.1	The Tenderer shall seal the original and all copies of the Tender in one inner envelopes and one outer envelope, duly marking the inner envelopes as “ORIGINAL” and “COPY”.

19.2	The inner and outer envelopes shall

(a)	be addressed to the Employer at the address provided in the Tender Data;

(b)	bear the name and identification number of the Contract as defined in the Tender and Contract Data; and

(c)	provide a warning not to open before the specified time and date for Tender opening as defined in the Tender Data.

19.3	In addition to the identification required in Sub-Clause 19.2, the inner envelopes shall indicate the name and address of the Tenderer to enable the Tender to be returned unopened in case it is declared late, pursuant to Clause 21.

19.4	If the outer envelope is not sealed and marked as above, the Employer will assume no responsibility for the misplacement or premature opening of the Tender.


	[bookmark: _Toc343309786][bookmark: _Toc55112531]20.	Deadline for Sub-mission of Tenders
	20.1	Tenders shall be delivered to the Employer at the address specified above no later than the time and date specified in the Tender Data.

20.2	The Employer may extend the deadline for submission of Tenders by issuing an amendment in accordance with Clause 10, in which case all rights and obligations of the Employer and the Tenderers previously subject to the original deadline will then be subject to the new deadline.


	[bookmark: _Toc343309787][bookmark: _Toc55112532]21.	Late Tenders
	21.1	Any Tender received by the Employer after the deadline prescribed in Clause 20 will be returned unopened to the Tenderer.


	[bookmark: _Toc343309788][bookmark: _Toc55112533]22.	Modification and Withdrawal of Tenders
	22.1	Tenderers may modify or withdraw their Tenders by giving notice in writing before the deadline prescribed in Clause 20.

22.2	Each Tenderer’s modification or withdrawal notice shall be prepared, sealed, marked, and delivered in accordance with Clauses 18 and 19, with the outer and inner envelopes additionally marked “MODIFICATION” or “WITHDRAWAL,” as appropriate.

22.3	No Tender may be modified after the deadline for submission of Tenders.

22.4	Withdrawal of a Tender between the deadline for submission of Tenders and the expiration of the period of Tender validity specified in the Tender Data or as extended pursuant to Sub-Clause 15.2 may result in the forfeiture of the Tender Security pursuant to Clause 16.

22.5	Tenderers may only offer discounts to, or otherwise modify the prices of their Tenders by submitting Tender modifications in accordance with this clause, or included in the original Tender submission.



[bookmark: _Toc343309789][bookmark: _Toc55112534]
E.  Tender Opening and Evaluation

	[bookmark: _Toc343309790][bookmark: _Toc55112535]23.	Tender Opening
	23.1	The Employer will open the Tenders, including modifications made pursuant to Clause 22, in the presence of the Tenderers’ representatives who choose to attend at the time and in the place specified in the Tender Data.

23.2	Envelopes marked “WITHDRAWAL” shall be opened and read out first.  Tenders for which an acceptable notice of withdrawal has been submitted pursuant to Clause 22 shall not be opened.

23.3	The Tenderers’ names, the Tender prices, the total amount of each Tender and of any alternative Tender (if alternatives have been requested or permitted), any discounts, Tender modifications and withdrawals, the presence or absence of Tender Security, and such other details as the Employer may consider appropriate, will be announced by the Employer at the opening.

23.4	The Employer will prepare minutes of the Tender opening, including the information disclosed to those present in accordance with Sub-Clause 23.3.


	[bookmark: _Toc343309791][bookmark: _Toc55112536]24.	Process to Be Confidential
	24.1	Information relating to the examination, clarification, evaluation, and comparison of Tenders and recommendations for the award of a contract shall not be disclosed to Tenderers or any other persons not officially concerned with such process until the award to the successful Tenderer has been announced.  Any effort by a Tenderer to influence the Employer’s processing of Tenders or award decisions may result in the rejection of his Tender.


	[bookmark: _Toc343309792][bookmark: _Toc55112537]25.	Clarification of Tenders
	25.1	To assist in the examination, evaluation, and comparison of Tenders, the Employer may, at the Employer’s discretion, ask any Tenderer for clarification of the Tenderer’s Tender, including breakdowns of unit rates.  The request for clarification and the response shall be in writing or by cable, telex, facsimile, or email but no change in the price or substance of the Tender shall be sought, offered, or permitted except as required to confirm the correction of arithmetic errors discovered by the Employer in the evaluation of the Tenders in accordance with Clause 27.


	[bookmark: _Toc343309793][bookmark: _Toc55112538]26.	Examination of Tenders and Determination of Responsiveness
	26.1	Prior to the detailed evaluation of Tenders, the Employer will determine whether each Tender (a) meets the eligibility criteria defined in Clause 3; (b) has been properly signed; (c) is accompanied by the required securities; and (d) is substantially responsive to the requirements of the Tender documents.

26.2	A substantially responsive Tender is one, which conforms to all the terms, conditions, and specifications of the Tender documents, without material deviation or reservation.  A material deviation or reservation is one (a) which affects in any substantial way the scope, quality, or performance of the Works; (b) which limits in any substantial way, inconsistent with the Tender documents, the Employer’s rights or the Tenderer’s obligations under the Contract; or (c) whose rectification would affect unfairly the competitive position of other Tenderers presenting substantially responsive Tenders.

26.3	If a Tender is not substantially responsive, it will be rejected by the Employer, and may not subsequently be made responsive by correction or withdrawal of the nonconforming deviation or reservation.


	[bookmark: _Toc343309794][bookmark: _Toc55112539]27.	Correction of Errors
	27.1	Tenders determined to be substantially responsive will be checked by the Employer for any arithmetic errors.  Errors will be corrected by the Employer as follows:
(a)	where there is a discrepancy between the amounts in figures and in words, the amount in words will govern; and

(b)	where there is a discrepancy between the unit rate and the line item total resulting from multiplying the unit rate by the quantity, the unit rate as quoted will govern, unless in the opinion of the Employer there is an obviously gross misplacement of the decimal point in the unit rate, in which case the line item total as quoted will govern, and the unit rate will be corrected.

27.2	The amount stated in the Tender will be adjusted by the Employer in accordance with the above procedure for the correction of errors and, with the concurrence of the Tenderer, shall be considered as binding upon the Tenderer.  If the Tenderer does not accept the corrected amount, the Tender will be rejected, and the Tender Security may be forfeited in accordance with Sub-Clause 16.6(b).


	[bookmark: _Toc343309795][bookmark: _Toc55112540]28.	Currency for Tender Evaluation
	28.1	Tenders will be evaluated as quoted in the currency of the Employer’s country as defined in the Contract Data in accordance with Sub-Clause 14.1, unless a Tenderer has used different exchange rates than those prescribed in Sub-Clause 14.2, in which case the Tender will be first converted into the amounts payable in different currencies using the rates quoted in the Tender and then reconverted to the Employer’s currency using the exchange rates prescribed in Sub-Clause 14.2.


	[bookmark: _Toc343309796][bookmark: _Toc55112541]29.	Evaluation and Comparison of Tenders
	29.1	The Employer will evaluate and compare only the Tenders determined to be substantially responsive in accordance with Clause 26.

29.2	In evaluating the Tenders, the Employer will determine for each Tender the evaluated Tender price by adjusting the Tender price as follows:

(a)	making any correction for errors pursuant to Clause 27;

(b)	excluding provisional sums and the provision, if any, for contingencies in the Bill of Quantities, but including Day work, where priced competitively;

(c)	making an appropriate adjustment for any other acceptable variations, deviations, or alternative offers submitted in accordance with Clause 17; and

(d)	making appropriate adjustments to reflect discounts or other price modifications offered in accordance with Sub-Clause 22.5.

29.3	The Employer reserves the right to accept or reject any variation, deviation, or alternative offer. Variations, deviations, and alternative offers and other factors, which are in excess of the requirements of the Tender documents or otherwise result in unsolicited benefits for the Employer will not be taken into account in Tender evaluation.

29.4	The estimated effect of any price adjustment conditions under Clause 47 of the Conditions of Contract, during the period of implementation of the Contract, will not be taken into account in Tender evaluation.


	[bookmark: _Toc343309797][bookmark: _Toc55112542]30.	Preference for Domestic Tenderers
	30.1	A percent margin of price preference of not less than 10% for qualifying domestic tenderers shall apply in tender evaluation in accordance with the criteria set by the Public Procurement Board for fixing such percentages. 

30.2	Domestic Tenderers shall provide all evidence necessary to prove that they meet the following criteria to be eligible for the specified percent margin of preference in the comparison of their Tenders with those of Tenderers who do not qualify for the preference.  They should

(a)	be registered within the country of the Employer;

(b)	have majority ownership by nationals of the country of the Employer;

(c)	not subcontract more than 50 percent of the Works measured in terms of value to foreign contractors; and

(d)	satisfy any other criteria specified for the purpose of domestic preference eligibility, as specified in the Tender Data.

30.3	Joint ventures between domestic and foreign firms may be eligible for the margin of preference provided the domestic partner or partners

(a)	individually satisfy the above criteria of eligibility for the preference;

(b)	demonstrate a beneficiary interest of no less than 50 percent in the joint venture, as demonstrated by the profit and loss sharing provisions of the joint venture agreement;

(c)	will, under the arrangements proposed, carry out at least 50 percent of the Works, measured in terms of value, which shall exclude any materials or plant which are to be directly imported by the domestic partner(s) (always provided that the domestic partner or partners are qualified to carry out that amount of work, in accordance with the criteria of Sub-Clause 4.3); and

(d)	satisfy any other criteria specified for the purpose of domestic preference eligibility, as specified in the Tender Data.

30.4	The following procedure will be used to apply the margin of preference:

(a)	Responsive Tenders will be classified into the following groups:

(i)	Group A:  Tenders offered by domestic Tenderers and joint ventures meeting the respective criteria of Sub-Clauses 30.2 and 30.3 above; and

(ii)	Group B:  all other Tenders.
(b)	For the purpose of further evaluation and comparison of Tenders only, an amount equal to 7½ percent of the evaluated Tender prices determined in accordance with Clause 29.2(a), (b), and (d), will be added to all Tenders classified in Group B.
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F.  Award of Contract

	[bookmark: _Toc343309799][bookmark: _Toc55112544]31.	Award Criteria
	31.1	Subject to Clause 32, the Employer will award the Contract to the Tenderer whose Tender has been determined to be substantially responsive to the Tender documents and who has offered the lowest evaluated Tender price, provided that such Tenderer has been determined to be (a) eligible in accordance with the provisions of Clause 3, and (b) qualified in accordance with the provisions of Clause 4.


	[bookmark: _Toc343309800][bookmark: _Toc55112545]32.	Employer’s Right to Accept any Tender and to Reject any or all Tenders
	32.1	Notwithstanding Clause 31, the Employer reserves the right to accept or reject any Tender, and to cancel the Tender process and reject all Tenders, at any time prior to the award of Contract, without thereby incurring any liability to the affected Tenderer or Tenderers or any obligation to inform the affected Tenderer or Tenderers of the grounds for the Employer’s action.


	[bookmark: _Toc343309801][bookmark: _Toc55112546]33.	Notification of Award and Signing of Agreement
	33.1	The Tenderer whose Tender has been accepted will be notified of the award by the Employer prior to expiration of the Tender validity period by cable, telex, email or facsimile confirmed by registered letter. This letter (hereinafter and in the Conditions of Contract called the “Letter of Acceptance”) will state the sum that the Employer will pay the Contractor in consideration of the execution, completion, and maintenance of the Works by the Contractor as prescribed by the Contract (hereinafter and in the Contract called the “Contract Price”).

33.2	The notification of award will constitute the formation of the Contract, subject to the Tenderer furnishing the Performance Security in accordance with Clause 34 and signing the Agreement in accordance with Sub-Clause 33.3.

33.3	The Agreement will incorporate all agreements between the Employer and the successful Tenderer.  It will be signed by the Employer and sent to the successful Tenderer, within 28 days following the notification of award along with the Letter of Acceptance.  Within 21 days of receipt, the successful Tenderer will sign the Agreement and deliver it to the Employer.

33.4	Upon the furnishing by the successful Tenderer of the Performance Security, the Employer will promptly notify the other Tenderers that their Tenders have been unsuccessful.


	[bookmark: _Toc343309802][bookmark: _Toc55112547]34.	Performance Security
	34.1	Within 28 days after receipt of the Letter of Acceptance, the successful Tenderer shall deliver to the Employer a Performance Security in the amount stipulated in the Contract Data and in the form (Bank Guarantee and/or Bond) stipulated in the Tender Data, denominated in the type and proportions of currencies in the Letter of Acceptance and in Accordance with the Conditions of Contract.

34.2	If the Performance Security is provided by the successful Tenderer in the form of a Bank Guarantee, it shall be issued either (a) at the Tenderer’s option, by a bank located in the country of the Employer or a foreign bank through a correspondent bank located in the country of the Employer, or (b) with the agreement of the Employer directly by a foreign bank acceptable to the Employer.


34.3	If the Performance Security is to be provided by the successful Tenderer in the form of a Bond, it shall be issued by a surety, which the Tenderer has determined to be acceptable to the Employer.

34.4	Failure of the successful Tenderer to comply with the requirements of Sub-Clause 34.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Tender Security.


	[bookmark: _Toc343309803][bookmark: _Toc55112548]35.	Advance Payment and Security
	35.1	The Employer will provide an Advance Payment on the Contract Price as stipulated in the Conditions of Contract, subject to a maximum amount, as stated in the Tender Data.


	[bookmark: _Toc343309804][bookmark: _Toc55112549]36.	Adjudicator
	36.1	The Employer proposes the person named in the Tender Data to be appointed as Adjudicator under the Contract, at an hourly fee specified in the Tender Data, plus reimbursable expenses.  If the Tenderer disagrees with this proposal, the Tenderer should so state in the Tender.  If, in the Letter of Acceptance, the Employer has not agreed on the appointment of the Adjudicator, the Adjudicator shall be appointed by the Appointing Authority designated in the Contract Data at the request of either party.
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37. Corrupt or Fraudulent     Practices 
	3 37.1 The Government of Ghana (GOG) requires that all Procurement Entities as well as Tenderers, Suppliers, Contractors and Consultants participating in contracts financed from the public funds of the Republic of Ghana, adhere to the highest ethical standards, both during the tendering process and throughout the execution of such contracts. The list of definitions set forth below involves the most common types of corrupt practices, but is not exhaustive. For this reason, the Public Procurement Board will also consider claims of similar nature involving alleged acts of corruption, in accordance with the established procedure.

(a). “Bribery” means the act of unduly offering, giving, receiving or soliciting anything of value to influence the process of procuring goods or services, selecting consultants, or executing contracts.
(b). “Extortion” or “Coercion” means the act attempting to influence the process of procuring goods or services, selecting consultants, or executing contracts by means of threats of injury to person, property or reputation.
(c). “Fraud” means the misrepresentation of information or facts for the purpose of influencing the process of procuring goods or services, selecting consultants, or executing contracts, to the detriment of the Procurement Entity/Purchaser or other participants.
(d). “Collusion” is an agreement between tenderers designed to result in tenders at artificial prices that are not competitive.  


37.2 If, in accordance with the administrative procedures of the Public Procurement Board, it is demonstrated that a government/public official, or anyone acting on his or her behalf, and/or a Tenderer in a procurement process or supplier/contractor during the execution of the contract carried out in connection with a project financed from the public funds of the Republic of Ghana has committed corrupt practices, the Public Procurement Board or the appropriate Tender review Board will: 
(a).           reject a proposal to award a contract in connection with the respective procurement process; and/or
(b).          declare a firm and/or its personnel directly involved in corrupt practices, temporarily or permanently ineligible to be awarded future contracts financed from the public funds of the Republic of Ghana.
37.3  The Tenderer shall disclose any commissions or fees that may have been paid or are to be paid to agents, representatives, or commission agents with respect to the tendering process or execution of the contract. The information disclosed must include at the name and address of the agent, representative, or commission agent, the amount and currency, and the purpose of the commission or fee. The information must be included in the Tender Submission Sheet.
37.4 Any communications between the Tenderer and the Purchaser related to matters of alleged fraud or corruption must be made in writing 
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                                                          TENDER DATA
                                 
                                       Instructions to Tenderers Clause Reference

	(2.1)
	The Employer is ELLEMBELLE DISTRICT ASSEMBLY


	(2.1)
	Project Name

CONSTRUCTION OF 1NO. MATERNITY BLOCK 1NO. AND 1NO. LABORATORY AND RADIOLOGY BLOCK AT NKROFUL

	(4.3)
	The information required from Tenderer in Sub-Clause 4.3 is modified as follows: 
(a) Valid Labour Certificate
(b) Valid Tax Clearance Certificate
(c) Valid Social Security and National Insurance Trust (SSNIT) Certificate
(d) Valid Certificate to Commence Business
(e) Valid Business Registration Certificate
(f) Ministry of Works and Housing
(g) Public Procurement Authority Registration Certificate 
(h) Evidence of past Work Experience


      

	(4.4)
	The qualification data required from Tenderer in Sub-Clause 4.4 are modified as follows: None

	(4.5)
	The qualification criteria in Sub-Clause 4.5 are modified as follows:   
 to includes;-
(a) Site Manager             – 1No.  Bsc BT  with 5yrs similar experience
(b) Quantity Surveyor     – 1No.  Bsc BT  with 5yrs similar experience
(c) Concrete Supervisor  – 1No.  CTC II  with 5yrs similar experience
(d) Accountant                – 1No.  HND      with 5yrs similar experience  
(e) Safety Officer            - 1No   HND      with 5yrs Similar   experience

	(4.5a)
	The minimum required annual volume of construction work for the successful Tenderer in any of the last five years shall be Seven Million Eight Hundred Thousand Ghana Cedis (GH¢7,800.000.00) Public Procurement Authority Registration Certificate 



	(4.5c)
	The minimum essential equipment to be made available for the Contract by the successful Tende./;rer shall be: 
(a) Backhoe                                              -       1 No
(b) Tipper Truck                                       –      2 No 
(c) Pedestrian Roller / Plate Compactor   –      1 No. 
(d) Concrete Mixer                                   –      2 No 
(e) Concrete Vibrator                               –      2 No.
(f) Bar Bender / Cutter                             –      1 set
                                        

	(4.5e)
	The minimum amount of liquid assets and/or credit facilities net of other contractual commitments of the successful Tenderer shall be One Million Three Hundred  Thousand Ghana Cedis ( GH¢ 1,300,000.00 )

	

(8.2)

	
The number of copies of the Tender to be completed and returned shall be: Two(2)  - One Original and one  photo copies

	(13.4)
	The Contract shall not be subject to price adjustment in accordance with Clause 47 of the Conditions of Contract. 

	(14.1)

(14.2)
	The specified international trading currency shall be Not applicable.

The date of the exchange rate is Not applicable

The authority for establishing the rates of exchange shall be Not applicable



	(15.1)
	The period of Tender validity shall be 120 days after the deadline for Tender submission specified in the Tender Data.


	(15.3)
	The adjustment of Tender price in accordance with Clause 15.3 shall be calculated on the basis of an annual increase for foreign costs of Zero percent and an annual increase for local costs of hundred percent.


	(16.1)
	The amount of Tender Security shall be 2.5% of tender price or an equivalent amount in a freely convertible currency and shall be in the form of Certified Cheque, Bank Draft, Bank Guarantee from a commercial Bank OR Tender Bond from an Insurance firm in good standing with the Ghana Insurance Commission.


	(17.0)
	Alternative proposals to the requirements of the Tender documents shall be permitted with respect to Clause 17.2.


	(19.2)
	The Employer’s address for the purpose of Tender submission is: 


ELLEMBELLE DISTRICT ASSEMBLY
P. O. BOX 34
NKROFUL



	(20.1)
	The deadline for submission of Tenders shall be:

Date :                10TH NOVEMBER 2026
 
Time:                 10:00 GMT



[bookmark: _Toc343309615]


	(30.0)
	Domestic contractors will not receive a margin of preference in Tender evaluation.


	(34.0)
	The Standard Form of Performance Security acceptable to the Employer shall be:                  Bank Guarantee (10%)  OR
                               Performance Bond (30%)


	(35.0)
	The Advance Payment shall be limited to Fifteen (15%) Percent of the Contract Price.


	(36.1)
	The Adjudicator proposed by the Employer is: 

Name       The President
Address:   Ghana Institution of Surveyor
                 Palma House,
                 P.O. Box GP 916,
                 Accra-Ghana
Tel:           021-220191

The hourly fee for this proposed Adjudicator shall be: As per the hourly rate of GhIS
  






Section II.  Forms of Tender, Qualification Information, Letter of Acceptance, and Agreement
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Contractor’s Tender

	
Notes on Form of Contractor’s Tender
The Tenderer shall fill in and submit this Tender form with the Tender. Additional details on the price should be inserted if the Tender is in various currencies.  If the Tenderer objects to the Adjudicator proposed by the Employer in the Tender documents, he should so state in his Tender, and present an alternative candidate, together with the candidate’s daily fees and biographical data, in accordance with Clause 36 of the Instructions to Tenderers.



TENDER FORM

Date: _______________

To:  ________________________

Address: ____________________
              _____________________
	  _____________________
	  _____________________

We offer to execute the ………………………………………………………………………in accordance with the Conditions of Contract accompanying this Tender for the Contract Price of_________________________________________________________________________

  __________________________________________________(Gh¢___________________)

The Contract shall be paid in the following currencies:

	Currency
	Percentage payable in currency
	Rate of exchange:  one foreign equals GHC ____________
	Inputs for which foreign currency is required

	(a)

(b)
	
	
	



The advance payment required is not applicable:

	Amount
	Currency

	(a)

(b)
	



We accept the appointment of _______________________ as the Adjudicator.   

Or

We do not accept the appointment of __________________________ as the Adjudicator, and propose instead that ______________________________ be appointed as Adjudicator, whose daily fees and biographical data are attached.

This Tender and your written acceptance of it shall constitute a binding Contract between us.  We understand that you are not bound to accept the lowest or any Tender you receive.

Commissions or gratuities, if any, paid or to be by us to agents relating to this Tender, and to contract execution if we are awarded the contract, are listed below:



	Name & Address of Agent
	Amount & Currency
	Purpose of Commission or Gratuity

	
	
	

	
	
	

	
	
	




We hereby confirm that this Tender complies with the Tender Validity and Tender Security required by the Tender documents and specified in the Tender Data.


Authorized Signature:  	
Name and Title of Signatory:  	
Name of Tenderer:  	
Address:  	



[bookmark: _Toc55111308]ATTACHMENTS TO THE TENDER

[bookmark: _Toc55111309]Attach. 1	Power of Attorney

[bookmark: _Toc55111310]Attach. 2	Tender Security

[bookmark: _Toc55111311]Attach. 3	Price Schedules

[bookmark: _Toc55111312]Attach. 4	Documentary Evidence of Tenderer’s Qualifications

[bookmark: _Toc55111313]Attach. 5	Others:
· [bookmark: _Toc55111314]Work Programme and Schedule
· [bookmark: _Toc55111315]List of Subcontractors (if applicable)
· [bookmark: _Toc55111316]Design Drawings, Calculations and Technical Alternatives
[bookmark: _Toc343309617][bookmark: _Toc55111317][bookmark: _Toc55111318]		
Qualification Information

	
Notes on Form of Qualification Information

The information to be filled in by Tenderers in the following pages will be used for purposes of post qualification or for verification of prequalification as provided for in Clause 4 of the Instructions to Tenderers.  This information will not be incorporated in the Contract.  Attach additional pages as necessary.  Pertinent sections of attached documents should be translated into English.  If used for prequalification verification, the Tenderer should fill in updated information only.




Qualification Information

	1.	Individual Tenderers or Individual Members of Joint Ventures
	1.1	Constitution or legal status of Tenderer: _________  [attach copy]

Place of registration: _________________________

Principal place of business: ____________________

Power of attorney of signatory of Tender: [attach]

1.2	Total annual volume of construction work performed in five years, in the internationally traded currency specified in the Tender Data: _________________________________________

1.3	Work performed as prime Contractor on works of a similar nature and volume over the last five years.  The values should be indicated in the same currency used for Item 1.2 above.  Also list details of work under way or committed, including expected completion date.



	Project name and country
	Name of client and contact person
	Type of work performed and year of completion
	Value of contract

	(a)

(b)
	
	
	



	
	1.4	Major items of Contractor’s Equipment proposed for carrying out the Works.  List all information requested below.  Refer also to Sub-Clause 4.3(c) of the Instructions to Tenderers.



	Item of equipment
	Description, make, and age (years)
	Condition (new, good, poor) and number available
	Owned, leased (from whom?), or to be purchased (from whom?)

	(a)

(b)
	



	
	



	
	1.5	Qualifications and experience of key personnel proposed for administration and execution of the Contract.  Attach biographical data.  Refer also to Sub-Clause 4.3(e) of the Instructions to Tenderers and Sub-Clause 9.1 of the Conditions of Contract.




	Position
	Name
	Years of experience (general)
	Years of experience in proposed position

	(a)

(b)
	
	
	




	
	1.6	Proposed subcontracts and firms involved.  Refer to Clause 7 of Conditions of Contract.




	Sections of the Works
	Value of subcontract
	Subcontractor
(name and address)
	Experience in similar work

	(a)

(b)
	
	
	




	
	1.7	Financial reports for the last three years:  balance sheets, profit and loss statements, auditors’ reports, etc.  List below and attach copies.

1.8	Evidence of access to financial resources to meet the qualification requirements:  cash in hand, lines of credit, etc.  List below and attach copies of support documents.

1.9	Name, address, and telephone, telex, and facsimile numbers of banks that may provide references if contacted by the Employer.

1.10	Information on current litigation in which the Tenderer is involved.



	Other party(ies)
	Cause of dispute
	Amount involved

	(a)

(b)
	
	



	
	1.11	Statement of compliance with the requirements of Sub-Clause 3.2 of the Instructions to Tenderers.

1.12	Proposed Programme (work method and schedule).  Descriptions, drawings, and charts, as necessary, to comply with the requirements of the Tender documents.


	2.	Joint Ventures
	2.1	The information listed in 1.1 - 1.11 above shall be provided for each partner of the joint venture.

2.2	The information in 1.12 above shall be provided for the joint venture.

2.3	Attach the power of attorney of the signatory(ies) of the Tender authorizing signature of the Tender on behalf of the joint venture.

2.4	Attach the Agreement among all partners of the joint venture (and which is legally binding on all partners), which shows that

(a)	all partners shall be jointly and severally liable for the execution of the Contract in accordance with the Contract terms;

(b)	one of the partners will be nominated as being in charge, authorized to incur liabilities, and receive instructions for and on behalf of any and all partners of the joint venture; and

(c)	the execution of the entire Contract, including payment, shall be done exclusively with the partner in charge.


	3.	Additional Requirements
	3.1	Tenderers should provide any additional information required in the Tender Data or to fulfill the requirements of Sub-Clause 4.1 and Clause 30 of the Instructions to Tenderers, if applicable.










LETTER OF ACCEPTANCE
[letter head paper of the Employer]
Date ______________

To: ______________________________

This is to notify you that your Tender dated _______ for execution of the ______________ for the Contract Price of the equivalent of _________________, ________________, as corrected and modified in accordance with the Instructions to Tenderers is hereby accepted by us.

We accept that ________________________ be appointed as the Adjudicator.

Or

We do not accept that ____________________ be appointed as adjudicator, and by sending a copy of this letter of acceptance to ___________________, we are hereby requesting _________________, the Appointing Authority, to appoint the Adjudicator in accordance with Clause 36.1 of the Instructions to Tenderers.

You are hereby required to submit the Performance Security stipulated in the Tender Documents within 28 days after receipt of this Letter of Acceptance. 

Following receipt of the Performance Security you will be invited to:

(i) sign the Contract Agreement as provided in the Tender Documents; and
(ii) to commence performance of the said contract in accordance with the   
            Contract Documents.

Authorized Signature ____________________________________________

Name and Title of Signatory _______________________________________

Name of Employer:  _____________________________________________

Attachment:  Agreement


Cc: Public Procurement Board and Relevant Departments.

Agreement

This Agreement, made the _____ day of _______, _______ between __________________________________________ (hereinafter called “the Employer”) and ______________________________________________________________________________________________________________________________________________________(hereinafter called “the Contractor”) of the other part.

Whereas the Employer is desirous that the Contractor execute ________________ (hereinafter called “the Works”) and the Employer has accepted the Tender by the Contractor for the execution and completion of such Works and the remedying of any defects therein.

Now this Agreement witnesseth as follows:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Conditions of Contract hereinafter referred to, and they shall be deemed to form and be read and construed as part of this Agreement.

2.	In consideration of the payments to be made by the Employer to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Employer to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

3.	The Employer hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects wherein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

In Witness whereof the parties thereto have caused this Agreement to be executed the day and year first before written.

	For the Employer
	For the Contractor

	Name:
	Name:

	Designation:
	Designation:

	Signature:
	Signature:

	
Witnessed by:
	
Witnessed by:

	Name:
	Name:

	Designation:
	Designation:

	Signature
	Signature
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Conditions of Contract

[bookmark: _Toc343309841]A.  General

	[bookmark: _Toc343309842]1.	Definitions
	1.1	Boldface type is used to identify defined terms.

The Adjudicator is the person appointed jointly by the Employer and the Contractor to resolve disputes in the first instance, as provided for in Clauses 24 and 25 hereunder.

Bill of Quantities means the priced and completed Bill of Quantities forming part of the Tender.

Compensation Events are those defined in Clause 44 hereunder.

The Completion Certificate is the certificate issued by the Project Manager after the Defects Liability Period and upon correction of all defects by the Contractor.

The Completion Date is the date of taking-over the Works as certified by the Project Manager, in accordance with Sub-Clause 55.1.

The Contract is the Contract between the Employer and the Contractor to execute, complete, and maintain the Works.  It consists of the documents listed in Clause 2.3 below.

The Contractor is a person or corporate body whose Tender to carry out the Works has been accepted by the Employer.

The Contractor’s Tender is the completed Tender document submitted by the Contractor to the Employer.

The Contract Price is the price stated in the Letter of Acceptance and thereafter as adjusted in accordance with the provisions of the Contract.

Days are calendar days; months are calendar months.

Dayworks are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant.

A Defect is any part of the Works not completed in accordance with the Contract.

The Defects Liability Certificate is the certificate issued by Project Manager upon correction of defects by the Contractor.

The Defects Liability Period is the period named in the Contract Data and calculated from the Taking-Over Date.

Drawings include calculations and other information provided or approved by the Project Manager for the execution of the Contract.

The Employer is the party who employs the Contractor to carry out the Works.

Equipment is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works.

The Initial Contract Price is the Contract Price listed in the Employer’s Letter of Acceptance.

The Intended Completion Date is the date on which it is intended that the Contractor shall substantially complete the Works.  The Intended Completion Date is specified in the Contract Data.  The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order.

Materials are all supplies, including consumables, used by the Contractor for incorporation in the Works.

Plant is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function.

The Project Manager is the person named in the Contract Data (or any other competent person appointed by the Employer and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract.

The Site is the area defined as such in the Contract Data.

Site Investigation Reports are those that were included in the Tender documents and are factual and interpretative reports about the surface and subsurface conditions at the Site.

Specification means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager.


The Start Date is given in the Contract Data.  It is the latest date when the Contractor shall commence execution of the Works.  It does not necessarily coincide with any of the Site Possession Dates.

A Subcontractor is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site.

The Taking-Over Certificate is a certificate issued by the Project Manager when the works are substantially completed in accordance with Sub-Clause 55.1

Temporary Works are works designed, constructed, installed, and removed by the Contractor that are needed for construction or installation of the Works.

A Variation is an instruction given by the Project Manager which varies the Works.

The Works are what the Contract requires the Contractor to construct, install, and turn over to the Employer, as defined in the Contract Data.


	[bookmark: _Toc343309843]2.	Interpretation
	2.1	In interpreting these Conditions of Contract, singular also means plural, male also means female or neuter, and the other way around.  Headings have no significance.  Words have their normal meaning under the language of the Contract unless specifically defined.  The Project Manager will provide instructions clarifying queries about these Conditions of Contract.

2.2	If sectional completion is specified in the Contract Data, references in the Conditions of Contract to the Works, the Completion Date, and the Intended Completion Date apply to any Section of the Works (other than references to the Completion Date and Intended Completion Date for the whole of the Works).

2.3	The documents forming the Contract shall be interpreted in the following order of priority:






(1)	Agreement,
(2)	Letter of Acceptance,
(3)	Contractor’s Tender,
(4)	Contract Data,
(5)	Conditions of Contract,
(6)	Specifications,
(7)	Drawings,
(8)	Bill of Quantities,[footnoteRef:1] and [1:  In lump sum contracts, delete “Bill of Quantities” and replace with “Activity Schedule”.] 

(9)	any other document listed in the Contract Data as forming part of the Contract.


	[bookmark: _Toc343309844]3.	Language and Law
	3.1	The Contract and the law governing the Contract shall be in English 


	4. [bookmark: _Toc343309845]Duties and Authority of the Project Manager

	4.1	(a) The Project Manager shall carry out the duties specified in the       Contract
(b) The Project Manager may exercise the authority specified in or necessarily to be implied from the Contract
(c)  Except as expressly stated in the Contract, the Project Manager shall have no authority to relieve the Contractor of any of his obligations under the Contract

4.2   With reference to Sub-Clause 4.1 (b), the following provision shall also apply:
The Project Manager shall obtain the specific approval of the Employer before taking any of the following actions:
(a) approving subcontracting of any part of the Works;
(b) certifying additional cost;
(c) determining an extension of time;
(d) issuing a variation under, except if such variation would    increase the Contract Price by less than the amount stated in the Appendix to Tender; or
(e) fixing rates or prices.

4.3  Except where otherwise specifically stated, the Project Manager will decide contractual matters between the Employer and the Contractor in the role representing the Employer.

4.4  Notwithstanding the obligation, as set out above, to obtain approval, if, in the opinion of the Project Manager, an emergency occurs affecting the safety of life or of the Works or of adjoining property, he may, without relieving the Contractor of any of his duties and responsibilities under the Contract, instruct the Contractor to execute all such work or to do all such things as may, in the opinion of the Project Manager, be necessary to abate or reduce the risk.  The Contractor shall forthwith comply, despite the absence of approval of the Employer, with any such instruction of the Project Manager. The Project Manager shall determine an addition to the Contract Price, in respect of such instruction, in consultation with the Employer and shall notify the Contractor accordingly, with a copy to the Employer


	[bookmark: _Toc343309846]5.	Delegation
	5.1	The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor.


	[bookmark: _Toc343309847]6.Communications
	6.1	Communications between parties that are referred to in the Conditions shall be effective only when in writing.  A notice shall be effective only when it is delivered.


	[bookmark: _Toc343309848]7.	Subcontracting
	7.1	The Contractor may subcontract with the approval of the Project Manager, but may not assign the Contract without the approval of the Employer in writing.  Subcontracting shall not alter the Contractor’s obligations.


	[bookmark: _Toc343309849]8.	Other Contractors
	8.1	The Contractor shall cooperate and share the Site with other contractors, public authorities, utilities, and the Employer between the dates given in the Schedule of Other Contractors, as referred to in the Contract Data.  The Contractor shall also provide facilities and services for them as described in the Schedule.  The Employer may modify the Schedule of Other Contractors, and shall notify the Contractor of any such modification.


	[bookmark: _Toc343309850]9.	Personnel
	9.1	The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the Contract Data, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager.  The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule.


9.2	If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven days and has no further connection with the work in the Contract.


	[bookmark: _Toc343309851]10.	Employer’s and Contractor’s Risks

	10.1	The Employer carries the risks, which this Contract states are Employer’s risks, and the Contractor carries the risks, which this Contract states are Contractor’s risks.


	[bookmark: _Toc343309852]11.	Employer’s Risks
	11.1	From the Start Date until the Defects Correction Certificate has been issued, the following are Employer’s risks:

(a)	The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to

(i)	use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works or

(ii)	negligence, breach of statutory duty, or interference with any legal right by the Employer or by any person employed by or contracted to him except the Contractor.

(b)	The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Employer or in the Employer’s design, or due to war or radioactive contamination directly affecting the country where the Works are to be executed.

11.2	From the Completion Date until the Defects Correction Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is an Employer’s risk except loss or damage due to

(a)	a Defect which existed on the Completion Date,

(b)	an event occurring before the Completion Date, which was not itself an Employer’s risk, or

(c)	the activities of the Contractor on the Site after the Completion Date.

	[bookmark: _Toc343309853]12.	Contractor’s Risks
	12.1	From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) which are not Employer’s risks are Contractor’s risks.


	[bookmark: _Toc343309854]13.	Insurance
	13.1	The Contractor shall provide, in the joint names of the Employer and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts and deductibles stated in the Contract Data for the following events which are due to the Contractor’s risks:

(a)	loss of or damage to the Works, Plant, and Materials;

(b)	loss of or damage to Equipment;

(c)	loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and

(d)	personal injury or death.

13.2	Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for the Project Manager’s approval before the Start Date.  All such insurance shall provide for compensation to be payable in the types and proportions of currencies required to rectify the loss or damage incurred.

13.3	If the Contractor does not provide any of the policies and certificates required, the Employer may effect the insurance which the Contractor should have provided and recover the premiums the Employer has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due.

13.4	Alterations to the terms of an insurance shall not be made without the approval of the Project Manager.

13.5	Both parties shall comply with any conditions of the insurance policies.


	[bookmark: _Toc343309855]14.	Site Investigation Reports
	14.1	The Contractor, in preparing the Tender, shall rely on any Site Investigation Reports referred to in the Contract Data, supplemented by any information available to the Tenderer.


	[bookmark: _Toc343309856]15.	Queries about the Contract Data

	15.1	The Project Manager will clarify queries on the Contract Data.


	[bookmark: _Toc343309857]16.	Contractor to Construct the Works
	16.1	The Contractor shall construct and install the Works in accordance with the Specifications and Drawings.



	[bookmark: _Toc343309858]17.	The Works to Be Completed by the Intended Completion Date

	17.1	The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Programme submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date.


	[bookmark: _Toc343309859]18.	Approval by the Project Manager
	18.1	The Contractor shall submit Specifications and Drawings showing the proposed Temporary Works to the Project Manager, who is to approve them if they comply with the Specifications and Drawings.

18.2	The Contractor shall be responsible for design of Temporary Works.

18.3	The Project Manager’s approval shall not alter the Contractor’s responsibility for design of the Temporary Works.

18.4	The Contractor shall obtain approval of third parties to the design of the Temporary Works, where required.

18.5	All Drawings prepared by the Contractor for the execution of the temporary or permanent Works, are subject to prior approval by the Project Manager before this use.


	[bookmark: _Toc343309860]19.	Safety
	19.1	The Contractor shall be responsible for the safety of all activities on the Site.


	[bookmark: _Toc343309861]20.	Discoveries
	20.1	Anything of historical or other interest or of significant value unexpectedly discovered on the Site shall be the property of the Employer. The Contractor shall notify the Project Manager of such discoveries and carry out the Project Manager’s instructions for dealing with them.


	[bookmark: _Toc343309862]21.	Possession of the Site
	21.1 Insofar as the Contract may prescribe the Employer shall give:
(a) 	the extent of portions of the Site of which the Contractor is to be given possession from time to time
(b) 	the order in which such portions shall be made available to the Contractor, and, subject to any requirement in the Contract as to the order in which the Works shall be executed, the Employer will, with the Project Manager's notice to commence the Works, give to the Contractor possession of
(c) 	so much of the Site, and
(d) 	such access as, in accordance with the Contract, is to be provided by the Employer as may be required to enable the Contractor to commence and proceed with the execution of the Works in accordance with the programme referred to in Clause 27, if any, and otherwise in accordance with such reasonable proposals as the Contractor ' shall, by notice to the Project Manager with a copy to the Employer, make. The Employer will, from time to time as the Works proceed, give to the Contractor possession of such further portions of the Site as may be required to enable the Contractor to proceed with the execution of the Works with due dispatch in accordance with such programme or proposals, as the case may be.


	[bookmark: _Toc343309863]22.	Access to the Site
	22.1	The Contractor shall allow the Project Manager and any person authorized by the Project Manager access to the Site and to any place where work in connection with the Contract is being carried out or is intended to be carried out.


	[bookmark: _Toc343309864]23.	Instructions
	23.1	Pursuant to the Duties and Authority of the Project Manager as specified in Clause 4, the Contractor shall carry out all instructions of the Project Manager, which comply with the applicable laws where the Site is located.


	[bookmark: _Toc343309865]24.	Disputes
	24.1	If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within 14 days of the notification of the Project Manager’s decision.


	[bookmark: _Toc343309866]25.	Procedure for Disputes
	25.1	The Adjudicator shall give a decision in writing within 28 days of receipt of a notification of a dispute.

25.2	The Adjudicator shall be paid by the hour at the rate specified in the Tender Data and Contract Data, together with reimbursable expenses of the types specified in the Contract Data, and the cost shall be divided equally between the Employer and the Contractor, whatever decision is reached by the Adjudicator.  Either party may refer a decision of the Adjudicator to an Arbitrator within 28 days of the Adjudicator’s written decision.  If neither party refers the dispute to arbitration within the above 28 days, the Adjudicator’s decision will be final and binding.

25.3	The arbitration shall be conducted in accordance with the arbitration procedure published by the institution named and in the place shown in the Contract Data.


	[bookmark: _Toc343309867]26.	Replacement of Adjudicator
	26.1	Should the Adjudicator resign or die, or should the Employer and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the Employer and the Contractor.  In case of disagreement between the Employer and the Contractor, within 30 days, the Adjudicator shall be designated by the Appointing Authority designated in the Contract Data at the request of either party, within 14 days of receipt of such request.




[bookmark: _Toc343309868]B.  Time Control

	[bookmark: _Toc343309869]27.	Programme

	27.1	Within the time stated in the Contract Data, the Contractor shall submit to the Project Manager for approval a Programme showing the general methods, arrangements, order, and timing for all the activities in the Works.

27.2	An update of the Programme shall be a Programme showing the actual progress achieved on each activity and the effect of the progress achieved on the timing of the remaining work, including any changes to the sequence of the activities.

27.3	The Contractor shall submit to the Project Manager for approval an updated Programme at intervals no longer than the period stated in the Contract Data.  If the Contractor does not submit an updated Programme within this period, the Project Manager may withhold the amount stated in the Contract Data from the next payment certificate and continue to withhold this amount until the next payment after the date on which the overdue Programme has been submitted.

27.4	The Project Manager’s approval of the Programme shall not alter the Contractor’s obligations.  The Contractor may revise the Programme and submit it to the Project Manager again at any time.  A revised Programme shall show the effect of Variations and Compensation Events.


	[bookmark: _Toc343309870]28.	Extension of the Intended Completion Date
	28.1	The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost.

28.2	The Project Manager shall decide whether and by how much to extend the Intended Completion Date within 21 days of the Contractor asking the Project Manager for a decision upon the effect of a Compensation Event or Variation and submitting full supporting information.  If the Contractor has failed to give early warning of a delay or has failed to cooperate in dealing with a delay, the delay by this failure shall not be considered in assessing the new Intended Completion Date.


	[bookmark: _Toc343309871]29.	Acceleration
	29.1	When the Employer wants the Contractor to finish before the Intended Completion Date, the Project Manager will obtain priced proposals for achieving the necessary acceleration from the Contractor. If the Employer accepts these proposals, the Intended Completion Date will be adjusted accordingly and confirmed by both the Employer and the Contractor.

29.2	If the Contractor’s priced proposals for an acceleration are accepted by the Employer, they are incorporated in the Contract Price and treated as a Variation.


	[bookmark: _Toc343309872]30.	Delays Ordered by the Project Manager

	30.1	The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works.


	[bookmark: _Toc343309873]31.	Management Meetings
	31.1	The Project Manager shall arrange monthly management meetings. The business of a management meeting shall be to review the plans for remaining work and to deal with matters raised in accordance with the early warning procedure.

31.2	The Project Manager shall record the business of management meetings and provide copies of the record to those attending the meeting and to the Employer.  The responsibility of the parties for actions to be taken shall be decided by the Project Manager either at the management meeting or after the management meeting and stated in writing to all who attended the meeting.


	[bookmark: _Toc343309874]32.	Early Warning
	32.1	The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price or delay the execution of the Works.  The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible.

32.2	The Contractor shall cooperate with the Project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone involved in the work and in carrying out any resulting instruction of the Project Manager.











[bookmark: _Toc343309875]C.  Quality Control

	[bookmark: _Toc343309876]33.	Identifying Defects
	33.1	The Project Manager shall check the Contractor’s work and notify the Contractor of any Defects that are found.  Such checking shall not affect the Contractor’s responsibilities.  The Project Manager may instruct the Contractor to search for a Defect and to uncover and test any work that the Project Manager considers may have a Defect.


	[bookmark: _Toc343309877]34.	Tests
	34.1	If the Project Manager instructs the Contractor to carry out a test not specified in the Specification to check whether any work has a Defect and the test shows that it does, the Contractor shall pay for the test and any samples.  If there is no Defect, the test shall be a Compensation Event.

	[bookmark: _Toc343309878]35.	Correction of Defects
	35.1	The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Taking-Over, and is defined in the Contract Data.  

35.2	Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice.


	[bookmark: _Toc343309879]36.	Uncorrected Defects
	36.1	If the Contractor has not corrected a Defect within the Defects Liability Period, the Project Manager will have the Defects corrected and the Contractor surcharged with the amount involved.




[bookmark: _Toc343309880]
D.  Cost Control

	[bookmark: _Toc343309881]37.	Bill of Quantities[footnoteRef:2] [2:  In lump sum contracts, delete “Bill of Quantities” and replace with “Activity Schedule,” and replace Sub-Clauses 37.1 and 37.2, as follows:
37.1	The Contractor shall provide updated Activity Schedules within 14 days of being instructed to by the Project Manager.  The activities on the Activity Schedule shall be coordinated with the activities on the Program.
37.2	The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately.] 

	37.1	The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor.

37.2	The Bill of Quantities is used to calculate the Contract Price.  The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item.


	[bookmark: _Toc343309882]38.	Changes in the Quantities[footnoteRef:3] [3:  In lump sum contracts, delete “Bill of Quantities” and replace with “Activity Schedule,” and replace entire Clause 38 with new Sub-Clause 38.1, as follows:
38.1	The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion.  Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule.] 

	38.1	If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than 25 percent, provided the change exceeds 1 percent of the Initial Contract Price, the Project Manager shall adjust the rate to allow for the change.

38.2	The Project Manager shall not adjust rates from changes in quantities if thereby the Initial Contract Price is exceeded by more than 15 percent, except with the prior approval of the Employer.

38.3	If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities.


	[bookmark: _Toc343309883]39.	Variations
	39.1	All Variations shall be included in updated Programmes[footnoteRef:4] produced by the Contractor. [4:  In lump sum contracts, add “and Activity Schedules” after “Programs”.] 



	[bookmark: _Toc343309884]40.	Payments for Variations
	40.1	The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager.  The Project Manager shall assess the quotation, which shall be given within seven days of the request or within any longer period stated by the Project Manager and before the Variation is ordered.
40.2	If the work in the Variation corresponds with an item description in the Bill of Quantities and if, in the opinion of the Project Manager, the quantity of work above the limit stated in Sub-Clause 38.1 or the timing of its execution do not cause the cost per unit of quantity to change, the rate in the Bill of Quantities shall be used to calculate the value of the Variation.  If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work.[footnoteRef:5] [5:  In lump sum contracts, delete this paragraph.] 


40.3	If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs.

40.4	If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event.

40.5	The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning.


	[bookmark: _Toc343309885]41.	Cash Flow Forecasts
	41.1	When the Programme[footnoteRef:6] is updated, the Contractor shall provide the Project Manager with an updated cash flow forecast.  The cash flow forecast shall include different currencies, as defined in the Contract, converted as necessary using the Contract exchange rates. [6:  In lump sum contracts, add “or Activity Schedule” after “Program”.] 



	[bookmark: _Toc343309886]42.	Payment Certificates
	42.1	The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed less the cumulative amount certified previously.

42.2	The Project Manager shall check the Contractor’s monthly statement and certify the amount to be paid to the Contractor.

42.3	The value of work executed shall be determined by the Project Manager.

42.4	The value of work executed shall comprise the value of the quantities of the items in the Bill of Quantities completed.[footnoteRef:7] [7:  In lump sum contracts, replace this paragraph with the following:  “The value of work executed shall comprise the value of completed activities in the Activity Schedule.”] 


42.5	The value of work executed shall include the valuation of Variations and Compensation Events.

42.6	The Project Manager may exclude any item certified in a previous certificate or reduce the proportion of any item previously certified in any certificate in the light of later information.


	[bookmark: _Toc343309887]43.	Payments
	43.1	Payments shall be adjusted for deductions for advance payments and retention.  The Employer shall pay the Contractor the amounts certified by the Project Manager within 28 days of the date of each certificate.  If the Employer makes a late payment, the Contractor shall be paid interest on the late payment in the next payment.  Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing for each of the currencies in which payments are made.

43.2	If an amount certified is increased in a later certificate or as a result of an award by the Adjudicator or an Arbitrator, the Contractor shall be paid interest upon the delayed payment as set out in this clause.  Interest shall be calculated from the date upon which the increased amount would have been certified in the absence of dispute.

43.3	Unless otherwise stated, all payments and deductions will be paid or charged in the proportions of currencies comprising the Contract Price.

43.4	Items of the Works for which no rate or price has been entered in will not be paid for by the Employer and shall be deemed covered by other rates and prices in the Contract.


	[bookmark: _Toc343309888]44.	Compensation Events
	44.1	The following shall be Compensation Events:

(a)	The Employer does not give access to the Site as defined in Clause 21 by the Site Possession Date as stated in the Contract Data.

(b)	The Employer modifies the Schedule of Other Contractors in a way that affects the work of the Contractor under the Contract.

(c)	The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time.

(d)	The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects.

(e)	The Project Manager unreasonably does not approve a subcontract to be let.

(f)	Ground conditions are substantially more adverse than could reasonably have been assumed before issuance of the Letter of Acceptance from the information issued to Tenderers (including the Site Investigation Reports), from information available publicly and from a visual inspection of the Site.

(g)	The Project Manager gives an instruction for dealing with an unforeseen condition, caused by the Employer, or additional work required for safety or other reasons.

(h)	Other contractors, public authorities, utilities, or the Employer does not work within the dates and other constraints stated in the Contract, and they cause delay or extra cost to the Contractor.

(i)	The advance payment is delayed.

(j)	The effects on the Contractor of any of the Employer’s Risks.

(k)	The Project Manager unreasonably delays issuing a Certificate of Completion.

(l)	Other Compensation Events described in the Contract or determined by the Project Manager shall apply.

44.2	If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Contract Price shall be increased and/or the Intended Completion Date shall be extended.  The Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended.

44.3	As soon as information demonstrating the effect of each Compensation Event upon the Contractor’s forecast cost has been provided by the Contractor, it shall be assessed by the Project Manager, and the Contract Price shall be adjusted accordingly.  If the Contractor’s forecast is deemed unreasonable, the Project Manager shall adjust the Contract Price based on the Project Manager’s own forecast. The Project Manager will assume that the Contractor will react competently and promptly to the event.

44.4	The Contractor shall not be entitled to compensation to the extent that the Employer’s interests are adversely affected by the Contractor’s not having given early warning or not having cooperated with the Project Manager.


	[bookmark: _Toc343309889]45.	Tax
	45.1	The Project Manager shall adjust the Contract Price if taxes, duties, and other levies are changed between the date 28 days before the submission of Tenders for the Contract and the date of the last Completion certificate.  The adjustment shall be the change in the amount of tax payable by the Contractor, provided such changes are not already reflected in the Contract Price or are a result of Clause 47.


	[bookmark: _Toc343309890]46.	Currencies
	46.1	Where payments are made in currencies other than the Ghanaian Cedis-, the exchange rates used for calculating the amounts to be paid shall be the exchange rates stated in the Contractor’s Tender.


	[bookmark: _Toc343309891]47.	Price Adjustment
	47.1	Prices shall be adjusted for fluctuations in the cost of inputs only if provided for in the Contract Data.  If so provided, the amounts certified in each payment certificate, after deducting for Advance Payment, shall be adjusted by applying the respective price adjustment factor to the payment amounts due in each currency.  A separate formula of the type indicated below applies to each Contract currency:

Pc = Ac + Bc  Imc/Ioc

where:

Pc is the adjustment factor for the portion of the Contract Price payable in a specific currency “c”.
Ac and Bc are coefficients[footnoteRef:8] specified in the Contract Data, representing the nonadjustable and adjustable portions, respectively, of the Contract Price payable in that specific currency “c”; and [8:  The sum of the two coefficients Ac and Bc should be 1 (one) in the formula for each currency.  Normally, both coefficients will be the same in the formulae for all currencies, since coefficient A, for the nonadjustable portion of the payments, is a very approximate figure (usually 0.15) to take account of fixed cost elements or other nonadjustable components.  The sum of the adjustments for each currency are added to the Contract Price.] 


Imc is the index prevailing at the end of the month being invoiced and Ioc is the index prevailing 28 days before Tender opening for inputs payable; both in the specific currency “c”.

47.2	If the value of the index is changed after it has been used in a calculation, the calculation shall be corrected and an adjustment made in the next payment certificate.  The index value shall be deemed to take account of all changes in cost due to fluctuations in costs.

	[bookmark: _Toc343309892]48.	Retention
	48.1	The Employer shall retain[footnoteRef:9] from each payment due to the Contractor the proportion stated in the Contract Data until Completion of the whole of the Works. [9:  The maximum retention amount is usually 5 percent of the Contract Price and in any case the retention on an Interim Certificate should not exceed 10 percent of its value.] 


48.2	On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected.

48.3	On completion of the whole Works, the Contractor may substitute retention money with an “on demand” Bank guarantee.


	[bookmark: _Toc343309893]49.	Liquidated Damages
	49.1	The Contractor shall pay liquidated damages[footnoteRef:10] to the Employer at the rate per day stated in the Contract Data for each day that the Completion Date is later than the Intended Completion Date.  The total amount of liquidated damages shall not exceed the amount defined in the Contract Data.  The Employer may deduct liquidated damages from payments due to the Contractor.  Payment of liquidated damages shall not affect the Contractor’s liabilities. [10:  Usually liquidated damages are set between 0.05 percent and 0.10 percent per day, and the total amount is not to exceed between 5 percent and 10 percent of the delayed portion of the works.] 


49.2	If the Intended Completion Date is extended after liquidated damages have been paid, the Project Manager shall correct any overpayment of liquidated damages by the Contractor by adjusting the next payment certificate.  The Contractor shall be paid interest on the overpayment, calculated from the date of payment to the date of repayment, at the rates specified in Sub-Clause 43.1.


	
	

	[bookmark: _Toc343309895]50.	Advance Payment
	50.1	The Employer shall make advance payment to the Contractor of the amounts stated in the Contract Data by the date stated in the Contract Data, against provision by the Contractor of an Unconditional Bank Guarantee in a form and by a bank acceptable to the Employer in amounts and currencies equal to the advance payment.  The Guarantee shall remain effective until the advance payment has been repaid, but the amount of the Guarantee shall be progressively reduced by the amounts repaid by the Contractor.  Interest will not be charged on the advance payment.

50.2	The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilization expenses required specifically for execution of the Contract.  The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager.

50.3	The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, following the schedule of completed percentages of the Works on a payment basis.  No account shall be taken of the advance payment or its repayment in assessing valuations of work done, Variations, price adjustments, Compensation Events, Bonuses, or Liquidated Damages.


	[bookmark: _Toc343309896]51.	Securities
	51.1	The Performance Security shall be provided to the Employer no later than the date specified in the Letter of Acceptance and shall be issued in an amount and form and by a bank or surety acceptable to the Employer, and denominated in the types and proportions of the currencies in which the Contract Price is payable.  The Performance Security shall be valid until a date 28 days from the date of issue of the Certificate of Completion in the case of a Bank Guarantee, and until one year from the date of issue of the Completion Certificate in the case of a Performance Bond.


	[bookmark: _Toc343309897]52.	Dayworks
	52.1	If applicable, the Dayworks rates in the Contractor’s Tender shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way.

52.2	All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager.  Each completed form shall be verified and signed by the Project Manager within two days of the work being done.

52.3	The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms.


	[bookmark: _Toc343309898]53.	Cost of Repairs
	53.1	Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions.


[bookmark: _Toc343309899]

E.  Finishing the Contract

	[bookmark: _Toc343309900]54.	Completion
	54.1	The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager will do so upon deciding that the work is completed.


	[bookmark: _Toc343309901]55.	Taking Over
	55.1	The Employer shall take over the Site and the Works within seven days of the Project Manager’s issuing a certificate of Completion.


	[bookmark: _Toc343309902]56.	Final Account
	56.1	The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period.  The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within 56 days of receiving the Contractor’s account if it is correct and complete.  If it is not, the Project Manager shall issue within 56 days a schedule that states the scope of the corrections or additions that are necessary.  If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate.

	[bookmark: _Toc343309903]57.	Operating and Maintenance Manuals
	57.1	If “as built” Drawings and/or operating and maintenance manuals are required, the Contractor shall supply them by the dates stated in the Contract Data.

57.2	If the Contractor does not supply the Drawings and/or manuals by the dates stated in the Contract Data, or they do not receive the Project Manager’s approval, the Project Manager shall withhold the amount stated in the Contract Data from payments due to the Contractor.


	[bookmark: _Toc343309904]58.	Termination
	58.1	The Employer or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract.

58.2	Fundamental breaches of Contract shall include, but shall not be limited to, the following:

(a)	the Contractor stops work for 28 days when no stoppage of work is shown on the current Programme and the stoppage has not been authorized by the Project Manager;

(b)	the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within 28 days;

(c)	the Employer or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation;

(d)	a payment certified by the Project Manager is not paid by the Employer to the Contractor within 84 days of the date of the Project Manager’s certificate;

(e)	the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager;

(f)	the Contractor does not maintain a Security, which is required; and

(g)	the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the Contract Data.

58.3	When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under Sub-Clause 59.2 above, the Project Manager shall decide whether the breach is fundamental or not.

58.4	Notwithstanding the above, the Employer may terminate the Contract for convenience.

58.5	If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible.


	[bookmark: _Toc343309905]59.	Payment upon Termination
	59.1	If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Contract Data. Additional Liquidated Damages shall not apply.  If the total amount due to the Employer exceeds any payment due to the Contractor, the difference shall be a debt payable to the Employer.

59.2	If the Contract is terminated for the Employer’s convenience or because of a fundamental breach of Contract by the Employer, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate.


	[bookmark: _Toc343309906]60.	Property
	60.1	All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Employer if the Contract is terminated because of the Contractor’s default.


	[bookmark: _Toc343309907]61.	Release from Performance
	61.1	If the Contract is frustrated by the outbreak of war or by any other event entirely outside the control of either the Employer or the Contractor, the Project Manager shall certify that the Contract has been frustrated.  The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made.
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The following documents are also part of the Contract:

Contract
   Clause
	1.0
	The Site is located at construction of 1no.Maternity block and 1No.Laboratory block and 1No.Radiology block at Nkroful


	1.1
	The Employer is:
                   
Name: 	           ELLEMBELLE DISTRICT ASSEMBLY

Address: 	P. O. BOX 34
         
Town:		NKROFUL

Name of Authorized Representative: DISTRICT CHIEF EXECUTIVE
  
The Project Manager-(Consultant) is:

Name:		District Works Department

Address:	ELLEMBELLE DISTRICT ASSEMBLY, 
                        P. O. Box 34
                        
Town:	            NKROFUL

Name of Authorized Representative: District Engineer
 The name and identification number of the Contract is: Construction of 1no.Maternity block and 1No.Laboratory block and 1No.Radiology block at Nkroful
.
The Works consist of :
a. Site clearance 
b. Excavation 
c. Concrete Works 
d. Block Works
e. Carpentry Works
f. Plastering
g. Painting/decoration
h. Electrical Works
i. External Works

The Start Date shall be: 14 days after taking possession of the site.

The Intended Completion Date for the whole of the Works shall be
Calender (12) months after the Start Date.

The following documents also form part of the Contract: 
· Letter of Acceptance
· Forms of Bid and Qualification Information
· Contract Data
· General Conditions of Contract
· Specifications
· Drawings
· Priced BOQ
· Forms of Security
· Other documents as listed in the Tender Data


	3.0
	The language of the Contract documents is English.

The law that applies to the Contract is the law of the Republic of Ghana.


	8.0
	Schedule of Other Contractors


	9.0
	The Schedule of Key Personnel


	13.0
	The minimum insurance covers shall be:
(a) The maximum deductible for insurance of the Works and of Plant and Materials is Two thousand Ghana Cedis.

(b)	The minimum cover for insurance of the Works and of Plant and Materials in respect of the Contractor’s faulty design is Contract price + 15% of contract price to cover professional fees + cost of equipment

(c)	The maximum deductible for insurance of Equipment is One Thousand Ghana cedis

(d)	The minimum cover for loss or damage to Equipment is Contract price + 15% of contract price to cover professional fees

(d) The maximum deductible for insurance of other property is Five hundred Ghana cedis.
(e) The minimum for insurance of other property is as determined by Land Valuation Board or any statutory enactment.





(g)	The minimum cover for personal injury or death insurance

(i)	for the Contractor’s employees is According to Workmen’s Compensation Act.

(iii) and for other people is One Thousand Ghana cedis

	14.0
	Site Investigation Reports


	21.0
	The Site Possession Date shall be 14 days after signing the contract


	25.0
	Institution whose arbitration procedures shall be used: Ghana Institution of Surveyors (GhIS)

Fees and types of reimbursable expenses to be paid to the Adjudicator: in accordance with the scale of fees of the Ghana Institution of Surveyors.


	25.0
	Arbitration will take place in accordance with: rules and regulations of the Arbitration Act 38, 1961 of Ghana or any statutory re-enactment or amendment thereof for the time being in force.

	26.0
	Appointing Authority for the Adjudicator: The President of the Ghana Institution of Surveyors.


	27.0
	The Contractor shall submit a revised Programme for the Works within 15 days of delivery of the Letter of Acceptance.


	27.0
	The period between Programme updates is 30 days.

The amount to be withheld for late submission of an updated Programme is 2% of the interim certificate for the period determined for the preparation of the certificate.


	35.0
	The Defects Liability Period (DLP) is 180 days (6 months).


	41.0

	The Contractor shall submit an Updated Cash Flow Estimate for the Works within 30 days of delivery of the Letter of Acceptance.	        

	44.0
	The following events shall also be Compensation Events: None



	47.0
	The Contract shall not be subject to price adjustment in accordance with Clause 47 of the Conditions of Contract, and the following information regarding coefficients shall not apply.

(A) BIDDERS FOR ROADS AND MAJOR EARTHWORKS

 The formula is:
Pn = X + a(EL/ELo) + b(LL/LLo) + c(PL/PLo * FE/FEo) +d(FU/FUo)
+ e(BI/BIo) + f(CE/CEo) + G(RS/RSo) +h(CH/CHo) + i(TI/TIo) + j(PC/PCo) + k(MT/MTo) + l(MI/MIo), 
where Pn is the adjustment factor for the portion of the contract price payable in specific currency.
X, a, b, c, d, e, f, , g, h, i, j, k and l are coefficients described in Appendix “C” and “D”. EL, LL, PL, FE, FU, BI, CE, RS, CH, TI, PC, MT, and MI are current cost indices applicable to the elements of Expatriate Labour, Local Labour, Plant, Foreign Exchange, Fuel, Bitumen, Cement, Reinforcement Steel, Chippings, Timber, Precast Concrete, Marine Transport, and Miscellaneous Expenditure, and  ELo, LLo, PLo, FEo, FUo, BIo, CEo, RSo, CHo, TIo, PCo, MTo, and MIo are the corresponding indices at the beginning of adjustment period which is considered as 28 days before bid opening; and the indices are taken from the Ministry of Road Transport’s PMU’s Publications.

The following information regarding coefficients does apply:
(i) Bidders are to fill in their own weightings in Appendices “A” to the Contract Data. Appendix “B” is the Engineer’s Assessment of the weightings.
(ii) Bidders are to provide their own coefficients if they choose in Appendix “D”, but these should be within the permissible ranges. Appendix “C” is the Engineer’s Assessment of the coefficients.

(B) BIDDER FOR BUILDING WORKS CONSTRUCTION

The applicable Price adjustment factors are those published monthly in “CONSTRUCTION COST INDICES FOR 35 CONSTRUCTION WORKS ITEMS” by Building and Road Research Institute (BRRI), P.O. Box 40, UST Kumasi, Ghana; Telephone: +233 51 60064/5, Fax: 233 51 60080.


	
	The Index I for local currency will be (For Roads and dams: Indices provided by the Ministry of Road Transport, Project Management Unit, MRT/PMU; For buildings and Boreholes: Indices provided by Building and Road Research Institute (BRRI), P.O. Box 40, UST Kumasi, Tel. 051 60064/5,   Fax 05160080) 


	48.0
	The proportion of payments to be retained is 10 percent.


	49.0
	The liquidated damages for the whole of the Works are 0.05% of the final Contract Price per day.

The maximum amount of liquidated damages for the whole of the Works is 10 percent of the final Contract Price.


	50.0
	The Advance Payment shall not be applicable.


The Performance Security shall be for the following minimum amounts equivalent as a percentage of the Contract Price:

(a)	Bank Guarantee 10%.

(b)	Performance Bond 30%.

The standard form(s) of Performance Security acceptable to the Employer shall be Unconditional of the type presented in Section 8 of the Tender Documents.


	57.0
	Schedule of Operating and Maintenance Manuals


	57.0
	The date by which operating and maintenance manuals are required is None

The date by which “as built” drawings are required is: None.
The amount to be withheld for failing to produce “as built” drawings and/or operating and maintenance manuals by the date required is None
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1.GENERAL 

1.01 British Standards and Standard Codes of Practice. ……………………….…………
1.02 Contractors Plant Yard ………………………………………………………………
1.03 Approval of Suppliers of Materials and Goods ……………………………………..
1.04 Copies of Orders……………………………………………………………………..
1.05 Samples………………………………………………………………………………
1.06 Test Certificates……………………………………………………………………...
1.07 Progress Photographs………………………………………………………………...
1.08 Preservation of Survey Markers……………………………………………………..
1.09 Dimensions and Levels ……………………………………………………………..
1.010 Programme…………………………………………………………………………..


2. SITE DETAILS ……………………………………………………………………..…

2.01 Scope of Works …………………………………………………………………..…
2.02 Site of Works ……………………………… ……………………………………....
2.03 Land Available …………………………………………………………………..….
2.04 Royalties …………………………………………………………………………....
2.05 Possession of Site  ………………………………………………………………..…
2.06 Maintenance of Works Site………………………………………………………….
2.07 Temporary Access Tracks …………………………………………………………..

3. SURVEY AND SETTING OUT  ……..……………………………………………….

3.01 Setting out ………………………………………………………………………….. 
3.02 Agreement of Levels ………………………………………………………………..

4. MATERIALS TESTING……………………………………………………………….

4.01 Test Certificates for Materials and Manufactured Items Delivered to Site…………
4.02 Laboratory Testing …………………………………………………………………
4.03 Unsatisfactory Test Results…………………………………………………………

5. DEMOLITION AND SITE CLEARANCE……………………………………………

5.01 General Clearance………………………………………………………………….
5.02 Demolition of Structures……………………………………………………………
5.03 Objects below Original Surface…………………………………………………….
5.04 Reinstatement of Ground…………………………………………………………..
5.05 Disposal of Materials………………………………………………………………
5.06 Protection of Designated Trees…………………………………………………….



6. GENERAL EARTHWORKS                   –     Not Applicable

7. EXCAVATION AND FILLING              -     Not Applicable

8. MISCELLANEOUS EARTHWORKS    -     Not applicable


9. GENERAL STRUCTURRES                  –     Not Applicable
10.  CONCRETE

8.01 Inspection Before Concreting ………………………………………………….……..
8.02 Cement ……………….…………………………………………………………...…..
8.03 Storage of Cement …………..……………………………………………………….
8.04 Work Testing of Cement………………………………………………………….….
8.05 Aggregates………………………..…………………………………………………..
8.06 Storage of Aggregates …………………………………………………………….…
8.07 Work Testing of Aggregates……………………………………………………..…..
8.08 Water for Concrete……………………………………………………………..….…
8.09 Concrete…………………………………………………………………………….
8.010 Design of Mixes. …………………………………………………………………...
8.011 Trail Mixes………………………………………………………………………….
8.012 Measuring Material for Concrete…………………………………………………...
8.013 Water/Cement Ratio………………………………………………………………...
8.014 Works Test Cubes…………………………………………………………………...
8.015 Testing of Concrete for Consistency………………………………………………..
8.016 Mixing of Concrete …………………………………………………………………
8.017 Remixing of Concrete……………………………………………………………….
8.018 Placing of Concrete…………………………………………………………….
8.019 Compaction of Concrete ……………………………………………….…
8.020 Protection and Curing of Concrete…………………………………………………..
8.021 Cement Mortar……………………………………………………………………….
8.022 Construction Joints……………………………………………………………….….
8.023 Concrete Finish………………………………………………………………………

9. FRAMWORK

9.01 Formwork ………………………………………………………………………….
9.02 Formwork Tolerances  …………………………………………………………….
9.03 Class of Finish ………………………………………………………………….….
9.04 Formwork Stripping Times ………………………………………………………..
9.05 Formwork Treatment………………………………………………………………






	
10.  REINFORCEMENT

  10.01   Reinforcement ………………………………………………………………...
  10.02   Bending Schedules …………………………………………………………....
10.01 Bending of Reinforcement………………………………………………….…
10.02 Fixing of Reinforcement………………………………………………………
10.03 Spacer Blocks……………………………………………………………….…

11.    PRECAST CONCRETE

12.    MISCELLANEOUS STRUCTURES

 12.01        Scope of Works ………………………………………………………………
12.02 Surface Finish to In situ Concrete……………………………………………
12.03 Camber ………………………………………………………………………
12.04 Inserts ………………………………………………………………………..
12.05 Preparation to Prevent Adhesion…………………………………………….

12. BLOCKWORK

13.01   Blockwork Materials……………………………………………………………..
13.02   Mortar…………………………………………………………………………….
13.03   Blocks…………………………………………………………………………….
13.04   Workmanship……………………………………………………………………..
13.05   Wall Plaster…………………………………………………………..…………..

14 SHEET ROOFING

14.01  Aluminum Sheet Roofing	…………………………………………….……..
14.02  Galvanized Iron Sheet Roofing …………………………………..….….………..
14.03  Painting and Decoration………………………………………………..……..…..

15 STRUCTURAL TIMBER

16 PAINTING AND DECORATION

17     FENCING










	      





	
1. GENERAL

1.01.The terms “British Standards” (B.S.) and “British Standard Codes of Practice” (B.S.C.P.) shall refer to those documents published or issued by the British Standards Institute.

All such Standards and Codes of Practice referred to in the Specification or in the Bill of Quantities or in any Drawings or instructions forming part of the Contract or issued under the provisions of the Contract shall refer to the current editions including all amendments published up to date.

Materials and work to other Standards and Codes of Practice are admitted, provided that in the opinion of the Engineer, their requirements are not lower than those of B.S. & B.S.C.P., as referred to in the Contract Documents.

1.02 The Contractor’s Plant Yard or Quarries shall be used by the Contractor for his offices, stores, plant, workshops, latrines and messing accommodation: and the erection of temporary buildings or structures on the Site will not be allowed without the permission of the Engineer.

At the beginning of the Contract the plant yard or quarry shall be fenced off.  By the end of the Period of Maintenance the area and its environs shall be cleared of all construction equipment, materials, buildings and the like and shall be regarded and reinstated as directed by the Engineer.

1.03 Before entering into any Sub-contract for the supply of any materials or goods the Contractor shall obtain the Engineer’s approval in writing of the Sub-contractor from whom he proposes to obtain such materials or goods.  Should the Engineer at any time be dissatisfied with such materials or goods or with the method or operations carried out by such Sub-contractor’s work or place of business, the Engineer shall be empowered to cancel his previously given approval of such Sub-contractor.  The contractor shall them obtain such said materials or goods from such other supplier as may be approved by the Engineer and shall bear any additional cost thereof.

1.04 The Contractor and Sub-contractor shall provide the Engineer with copies of all orders, which they may place for the supply of materials or goods required in connection with the works.

1.05 In addition to any special provisions herein for the sampling and testing of materials, the Contractor shall submit to the Engineer as he may require samples of all materials and goods, which he proposes to use or employ in or for the Works.  Such samples, if approved, will be retained by the Engineer, and no materials or goods of which samples have been submitted shall be used on the Permanent Works unless and until such samples have been approved in writing by the Engineer.  Notwithstanding the Engineer’s approval as provided for herein the Contractor shall be solely responsible for the quality of all materials and goods supplied.


The cost of supplying all such samples and of conveying the same to such place of inspection or testing as the Engineer may designate within the country of origin and of complying with the requirements of this clause shall be deemed to be included in the tendered rates and prices.

1.06. Should the Engineer not inspect any materials or goods at the place of manufacture the Contractor shall obtain Certificates of Test from the suppliers of such goods and shall send such Certificates to the Engineer.  Such Certificates shall certify that the materials or goods concerned have been tested in accordance with the requirements of the Specification and shall give the results of the entire test carried out.  The Contractor shall provide adequate means of identifying the materials and goods delivered to the Site with the corresponding Certificates.

All costs incurred in complying with this Clause shall be deemed to be included in the tendered rates and prices.

1.07 The Contractor shall, if directed, provide a monthly photographic record of the execution of the Works with photographs taken by an approved photographer at such places as the Engineer may determine.  The Contactor will supply the Engineer with such proofs as he may require and three prints of each selected photograph together with the negative.  The prints are to be processed by an approved professional and shall be in colour, full plate size on heavy gloss paper.

1.08 Survey Markers shall where possible be preserved or else be relocated.  Where
survey markers will be destroyed, they shall be accurately referenced to permanent concrete markers before work is commenced.

1.09 Where dimensions and levels are shown on the Drawings or mentioned in the
documents forming part of or issued under the Contract there shall be verified by the Contractor on the site and he will be held responsible for pointing out promptly any errors or discrepancies in such dimensions or levels.

1.010  Further to Clauses 14.1 & 14.2 of the Conditions of Contract, the Contractor
shall provide with his tender a detailed programme of the order and the manner in which it is proposed to execute the Works.  The programme shall include time and progress charts to that the actual progress of each operation can be shown against anticipated progress.

Once approved by the Engineer the Programme shall be adhered to unless such alterations are found to be necessary during the construction of the work are confirmed in writing by the Engineer.  The Programme shall take into account the fluctuating seasonal rainfall.
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	2. SITE DETAILS

2.01 Details of the scope of the Works to be carried out under the Contact will be
given in Section 1.1 of the Contract Documents.

2.02 The precise location of the Works to be carried out under the Contact will be
given in Section 1.1 of the Contract Documents.


2.03  The Employer shall make available free of charge to the Contractor the land
on which the Works are to be executed or carried out.

Land required by the Contactor for his own camps, offices, houses, temporary works, spoil dumps, and the Engineer’s Office and Laboratory shall not be provided by the Employer and the Contractor shall provide such land at this own cost.

2.04 Possession of the Site will be given in accordance with Clause 11 of the
Conditions of Contract.

2.05 From the date of such possession of the Site until a certificate of completion has been given the Contractor shall be responsible for maintaining the Site in a satisfactory condition.

3. SURVEY AND SETTING OUT

3.01 In accordance with Clause 17.1 of the Conditions of Contact, the Contractor shall be responsible for the accurate setting out of the works in relation to original points, lines and levels of reference given by the Engineer in writing.

4.MATERIAL TESTING

4.01 When instructed by the Engineer the Contractor shall submit to him
Certificates of Test from the Suppliers of materials and manufactured articles to be used for the Contract.  Such Certificates shall certify that the materials and manufactured articles concerned have been tested in accordance with the requirements of the Specification and shall give the results of all the tests carried out.  The Contractor shall provide adequate means of identifying the materials and manufactured articles delivered to the Site with the corresponding Certificates.  Where such Certificate is not available a representative sample of the material shall be tested by an approved Laboratory or, subject to the approval of the Engineer, by the Contactor and a copy of the test results submitted to the Engineer who shall decide whether the material conforms to the required standards.

4.02 All testing carried out by the Contractor shall be undertaken at an approved
Laboratory manned by qualified staff.

All samples and records shall be preserved for as long as the Engineer may direct and they shall be kept and identified in an orderly manner to his satisfaction.   The laboratories, their equipment and all samples and records shall be open to inspection by the Engineer during normal working hours.

No separate payment shall be made to the Contactor in respect of his compliance with the requirements of this clause.  The costs of undertaking all laboratory tests shall be deemed to have been included in the various rates and prices entered by the Contactor in the Bill of Quantities.

4.03  Should the Engineer decide that the results of any specified or instructed
testing are unsatisfactory, he may order the stoppage of the work affected pending his further instruction.  Work in respect of which test results are unsatisfactory shall be liable to rejection and if so directed by the Engineer, such work shall be cut out and re-executed to the satisfaction of the Engineer.  The cost of all such stoppage, cutting out, making good and re-testing of the works affected shall be borne by the Contractor.

5. DEMOLITION AND SITE CLEARANCE

5.01 No clearance of or alteration to any main service or apparatus shall be done unless specifically ordered by the Engineer.

The Contractor shall grub up and remove all bushes undergrowth, trees, stumps, roots, anthills, ant’s nests, fences, rubbish, debris and other deleterious matter occurring within the Site of the Works or as otherwise directed by the Engineer.

5.02 Structures to be demolished shall be broken up and removed.  Prior to demolition the Contractor shall ensure that services have been disconnected to the satisfaction of the appropriate authorities and/or owners.

5.03 The Contractor shall prevent damage to trees which the Engineer may
designate to be preserved.  Such designated trees shall be protected from injury during continuance of the Contract.

6. EXCAVATION AND FILLING

6.01 Excavations
(a) Material whose strength is inadequate in relation to its depth below formation level shall be excavated from below formation level in cutting over such areas and such depth as directed by the Engineer.

(b) Where any material below original surface level beneath embankment is required to be excavated, it shall be removed to such depth and over such areas as are shown on the Drawings or as the Engineer shall direct and be disposed of in a manner depending on its nature and condition at the time.

(c) The method adopted by the Contractor for excavating soft materials below water in swamp areas shall be subject to the approval of the Engineer.

(d) Where embankments are to be constructed on steeply sloping ground, including the side slopes of existing embankments, existing sloping surfaces shall be excavated to form benching as directed by the Engineer.

6.02 Unsuitable material may be used, where directed by the Engineer, for flattening side slopes, filling depressions beyond the sides of embankments and in similar locations.



6.03 The Contractor shall make arrangements for and provide such spoil dump
as may be required for the disposal of evacuation of materials which are not to be incorporated in the Works.

7.CONCRETE

7.01 At the end of each day the Contactor shall give the Engineer a realistic
concreting programme for the next day.  Also notice shall be given to the Engineer when formwork and reinforcement are complete and ready to receive concrete at least six working hours before concrete is to be placed.


Before placing any concrete all shavings, loose binding wires, soil, rubbish and all foreign matter shall be removed from the formwork and the formwork shall carefully and thoroughly washed with water.  No concrete shall be placed until the Engineer has accepted the formwork and reinforcement.

7.02 Ordinary Portland Cement and Rapid Hardening Portland Cement shall
comply with B.S. 12.

7.03. Cement shall be stored in dry waterproof stores clear of the ground or in dry
waterproof silos.

7.04. Cement shall be tested sufficiently to ensure that it complies with the Specification.

7.05. Aggregates for concrete shall comply with B.S. 832.

7.06.  Each size of aggregate shall be stored separately and in such a way that it
shall not become contaminated with any deleterious and extraneous matter.  The aggregates shall be delivered to each concrete mixing plant and used in an unsegregated condition.

  The storage methods adopted shall allow the aggregates to drain freely

7.07. Tests on the aggregates shall be carried out in accordance with B.S. 812.  In
addition the moisture content of the aggregates shall be determined.

7.08. Water for concrete shall be clean, fresh and free from deleterious and 
extraneous matter, which in the opinion of the Engineer shall have a harmful effect on the Works.

As and when directed by the Engineer water for concrete will be tested in accordance with B.S. 3148.
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7.09  Concrete mixes shall be of the classes shown in the following table:-			
Concrete Class	Maximum 	Minimum 		     	Maximum 				Permissible 	Permissible			Permissible
			size of 		Compressive			Slump (mm)
			aggregate	Strength of 150 mm	
			(mm)		Works Cube in 
					N/sq.mm at 
					an age of
        					7days---28days
	1:4:8		37.5		-	   7.5			75		                1:2:4		37.5		15	   22.5			37.5			1:2:4		20		15	   22.5			37.5			1:1.5:3		37.5		20	   30			25		 	1:1.5:3		20		20	   30			25							
		
						
  
The cement content in any mix shall not exceed 540 kg/m3 unless agreed by the Engineer. The concrete mixes to be used in the various parts of the works shall be as stated in the Drawings or in the Specification or as otherwise directed by the Engineer.






The limits for salt contents of aggregates are subject to the overriding requirements tabulated in the following table:-

  Type of Mix		Total Acid Soluble 			Total Acid Soluble 				Chloride (as NaC1)			Sulphate (as SO3) 
			(% by weight of cement)		(% by weight of									cement)*													
Reinforced Concrete		0.15%				2.5%
Mass Concrete			1.00%				2.5%		

*Excluding the sulphate present in the cement			

7.10 The Contractor shall design the mixes to comply with the Specification and 
shall submit to the Engineer his proposed designs for provisional agreement.   The      
Contractor shall also submit to the Engineer samples (each weighing about 13 kg) 
of the fine and coarse aggregates he proposes to use.

7.11 Following approval of the mix design of each class of concrete by the Engineer the Contractor shall prepare a trail mix of each class of concrete in the presence of the Engineer.  Each trail mix shall comprise not less than a cubic meter of concrete and shall be mixed in a mechanical mixer of a type approved by the Engineer.
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	The quantities of all the ingredients of each trial max including water shall be carefully determined by weight according to the approved mix design and sieve analysis and shall be made by the method described in B.S. 812.

Six 150 mm test cubes shall be made by the Contractor in the presence of the Engineer from each trial mix.  The cubes shall be made, cured, stored and tested for their compressive strength at 28 days after manufacture all according to the method described in B.S. 1881. 

The Contractor shall redesign the mix and make a further trial mix and test cubes:- 

(a) If the value of the ultimate compressive strengths of any of the mix cubes less than the appropriate design strength, or 

(b) If the difference between the greatest and least compressive strengths of any of the six cubes of a set is greater than 15% of the average compressive strength of the six cubes, the Contractor shall allow ample time in his programme for designing and making trail mixes and the preparation and testing of compressive strength test cubes obtained therefrom.

7.12. Cement shall be measured by weight either by using a weighting machine or by making the size of each batch of concrete such as to require an integral number of bags of cement.

       Coarse and fine aggregates shall be measured separately by volume of weight.
       Water shall be measured by volume.

7.013 The water/cement ratios shall not be varied from the values, which have been accepted by the Engineer and shall be such that the concrete is just sufficiently workable to allow it to be compacted in accordance with the Specification.

7.14 Samples of concrete shall be taken, from which the works test cubes shall be 
made, as and where directed by the Engineer.

From each sample of concrete and at the place where the sample was taken six test cubes shall be made; 3 shall be tested at the age of 7 and 3 at the age of 28 days.

The test cubes shall be made, cured and tested in accordance with B.S. 1881.  The test cubes shall be tested at a laboratory approved by the Engineer or at the site laboratory.

If the results of the cube tests do not comply with the Specifications such remedial works as the Engineer may accept or direct shall be carried out.

7.15 Slump tests shall be carried out in accordance with B. S. 1881.



The frequency of the tests shall be that which the Engineer considers necessary to ensure that the consistency of the concrete is maintained in accordance with the accepted mix design.

7.16 Concrete shall be mixed in a power driven concrete mixer, of the type stated in the contractor’s mix design proposals, until such time as there is a uniform distribution of materials throughout the mix and the mix is uniform in colour and consistency.  Notwithstanding the foregoing the mixing time shall not be less than that recommended by the manufacturer of the concrete mixer.  The concrete mixer shall revolve at the speed recommended by the manufacturer.
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	7.17 Concrete, which has commenced to set, shall not be remixed either with or without additional water and in no case shall such concrete be used in the Works.

7.018 Placing and compaction of concrete shall be completed within 20 minutes of its leaving the mixer unless the concrete is transported in a revolving agitating drum kept continuously in motion.  Concrete shall be placed within 2 hours of the cement being introduced into the mix.

 Concrete shall be handled so that segregation of the constituent materials does not occur.

7.019 As concrete is placed in position in shall be compacted by using mechanical
vibrators in such a manner as to produce a dense, uniform and homogeneous mass free from voids and other imperfections.

Ample numbers of serviceable vibrators shall be available so as to ensure that the specifications are complied with even if vibrators failures occur.

During the placing and compaction of concrete for reinforced work a competent steel fixer and a carpenter shall be in constant attendance to adjust and correct, if necessary, the positions of the reinforcement of formwork.

Freshly placed concrete shall not be vibrated in such a manner as to cause damage to concrete in other parts of the Works which has already taken its initial set.  Concrete shall not be compacted to such an extent that segregation of the constituent materials occurs.

Concrete shall be placed in its final position and vibration shall not be used to facilitate spreading of concrete.

7.020 Immediately after placing, concrete shall be protected from the effects of adverse weather.

Concrete shall be cured for a period of not less than 7 days after placing by being kept constantly wet with water, which is free from deleterious and extraneous matter.

7.021 Cement mortar shall consist of 1 part by volume of Portland Cement to 3 parts by volume of the aggregate, unless otherwise specified, with a plasticising agent and just sufficient water to make the mortar workable consistent with its 
         purpose.

7.022  All vertical construction joints in all classes of work shall be formed by 
By inserting temporary stopping-ff boards to form a tongue and groove joint against which the concrete can be properly compacted.  When work is resumed against a vertical concrete surface, which has hardened or commenced to harden all laitance, porous and loose material and badly compacted concrete shall be removed from the old surface which shall then be brushed with a steel wire brush and thoroughly wetted.  The new concrete shall then be thoroughly compacted against the old.

When work is resumed against a horizontal concrete surface, which has hardened or commenced to harden the surface of the old concrete shall be roughened by hacking and all laitance shall be removed from it together with the porous layer below the laitance.

The surface shall then be swept clean and brushed, with a steel brush to remove all loose material, thoroughly wetted and covered with a layer of grout.  The grout material shall consist of cement mixed with sufficient water to give cement slurry.  The new concrete shall then be well compacted on top of the old.

7.023 Immediately after the removal of formwork all exposed bars or bolts passing 
through the reinforced concrete member and used for shuttering or any other purpose shall be cut to a depth of a t least 25 mm below the surface of the concrete.  All fins caused by form joints, all cavities produced by the removal of form ties and all other holes and depressions, broken edges or corners, and other defects shall be thoroughly cleaned, saturated with water, and carefully pointed and rendered true with mortar of cement and fine aggregate mixed in the same proportions as the grade of concrete which is being finished and of as dry a consistency as is compatible with its use.  Sufficient pressure shall be applied in filling and pointing to ensure thorough filling of all voids.  Surfaces, which have been pointed, shall be kept moist for a period of 24 hours.  Small areas of honeycombed concrete shall be cut out to a sufficient depth to expose solid concrete before being finished.

If honeycombing, in the opinion of the Engineer is of such an extent or character as to affect the strength of the structure materially or to endanger the life of the steel reinforcement, he may declare the concrete defective and require the removal and replacement of the portions of the structure affected.

Where shown on the Drawings exposed concrete shall be rubbed down to a smooth finish with a Carborundum stone dipped in cement grout.  Such work must be commenced within one hour of removing the formwork and completed in one operation.  Rubdown surfaces shall be fair faced, true to form and free from all board marks, joint marks, honeycombing, jutting etc.  The Contractor is permitted at his own expense to provide smooth lining to the forms, which will achieve this without rubbing down.  Rendering or cement washing on rubdown surfaces is not permitted.

8.  FORMWORK

8.01 Formwork shall mean the moulds for forming the concrete to the required shape 
together with the temporary construction required for the support of such moulds.

Formwork shall be constructed of materials of such quality and strength as to ensure rigidity throughout the placing, vibration, compaction, setting and hardening of the concrete such that there is no deflection which would damage the concrete or result in the finished line of the concrete not complying with the Drawings.

Formwork shall be sufficiently watertight to prevent any loss of liquid from the concrete and shall be capable of being removed without shock, vibration or damage to the concrete.  It shall be adequately propped and braced to resist any distortion by the pressure of the wet concrete.

Fair-faced formwork shall be used for exposed surfaces and shall be planted smooth and true, to form the surfaces, curves or shapes specified and joints shall be planed and perfectly watertight.

Rough formwork shall be used for unexposed surfaces and the timber may have a sawn finish but joints must be true and perfectly tight.

Should the Contractor wish to erect the formwork by passing ties through the work or embedding bolts therein, he must first obtain the approval of the Engineer’s Representative and when seeking such approval shall forward full details of the type of fitting proposed for the tie, and show how it will be employed in the work.  No type of fitting will be permitted which cannot be removed easily after use and which does not allow easy and effective making good of the concrete surface.  The use of wires requiring subsequent cutting into and plastering over the concrete will not be permitted.

Notwithstanding the foregoing, concrete surface finishes specified in the Drawings or this Specification shall also be subject to the following requirements:-



(1) (a) Class F1 Finish

This finish is for surfaces against which backfill or further concrete will be placed.  Formwork may be sawn boards, sheet metal or any other suitable materials, which will prevent the loss of fine material from the concrete being placed.

(b) Class F2 Finish

The irregularities in finish shall be no greater than those obtained from the use of wrought thickness square-edged boards arranged in a uniform pattern.  The finish is intended to be left as struck but imperfections such as fine and surface discolouration shall be made good to the satisfaction of the Engineer.

©  Class F3 Finish

The resulting finish shall be smooth and of uniform texture and appearance.  The formwork lining shall leave no stain on the concrete and shall be so joined and fixed to its backing that it imparts no blemishes.  It shall be of the dame type and obtained from only one source throughout any one structure.  The Contractor shall make good any imperfections in the finish to the satisfaction of the Engineer.  Internal ties and embedded metal parts will not be allowed.

(d) Class F4 Finish

The requirements for Class F4 Finish are as for Class F3 except that internal ties and embedded metal parts will be permitted.  The ties shall be positioned only in relates or in other positions as described in the contract or as agreed by the engineer.

                  (e) General Comments on Classes F2 – F4:
                  Permanently exposes concrete surfaces to Classes F2, F3 and F4 Finish 
                  shall be protected from rust marks and stains of all kinds.

Unless otherwise described in the Contract, all formwork joints for exposed surfaces of concrete to Class F2, F3 and F4 Finish shall form a regular pattern agreed by the Engineer with horizontal and vertical lines continuous throughout each structure and all construction joints shall coincide with these horizontal or vertical lines.

(2) Classes of Finish for Unformed Surfaces i.e. horizontal or nearly horizontal surfaces, and all other surfaces which are not cast against formwork

    (a)  Class UFI Finish
The concrete shall be uniformly leveled and screened in an approved manner by means of a steel-shod screed to produce a plain, textured or ridged surface as described in the Contract, and dense finish.  Care shall be taken to ensure that the surface of the concrete is properly “closed”.  No further work shall be applied to the surface unless it is used as the first stage for Class UF2 or Class UF3 Finish.



(b) Class UF2 Finish
After the concrete has hardened sufficiently, the concrete Class UF1 surface shall be floated by hand or machine sufficient only to produce a uniform surface free from screed marks.

© Class UF3 Finish
When the moisture film has disappeared and the concrete has hardened sufficiently to prevent laitance from being worked to the surface, a Class UF1 surface shall be lightly steel-trowelled under firm pressure to produce a dense, smooth uniform surface free from trowel marks.

8.02 The maximum permissible formwork tolerance shall be such as to ensure  
deviation of the concrete surface not greater than 3mm in 3 metres for permanently exposed surface and 12mm in 3 metres for surfaces not permanently exposed.  These tolerances shall not be cumulative.

8.03 The class of finish for exposed surfaces shall be class F2.  The irregularities in 
The finish shall be no greater than those obtained from the use of wrought thickness square edge boards arranged in a uniform pattern.  The finish is intended to be left as struck but imperfections such as fins and surfaces discolouration shall if required, be made good by methods approved by the Engineer’s Representative.

8.04 No formwork shall be removed without the Engineer prior approval and in no 
Case shall any shuttering or props be removed until the under-mentioned times have elapsed after placing the concrete.

Location of Formwork			Minimum Period

Beams sides, columns and walls			2days
Beam Soffits (props left under)			7 days
Beam props						14 days
Slab Soffits (props left under)				4 days
Slab Props 						10 days
   
8.05 All formwork for new lifts of concrete shall be tightly and accurately fitted 
Against the concrete already cast to ensure that the surface of the new work will be flush and in line with that of the old.

All formwork for exposed concrete surfaces shall be painted with an approved mould oil to prevent adhesion between concrete and formwork.

The mould shall be non-staining, insoluble in water, unharmful to the concrete, non-flaking and shall not be removable by rain or wash water.  The Contractor shall ensure that the oil shall be kept from contact with the reinforcement or embedded fittings.




9. REINFORCEMENT

9.01 The reinforcement bars shall be mild steel conforming to B.S. 4449.  Reinforcement mesh shall be mild steel welded mesh complying with B.S. 4483.

9.02 The Engineer will provide the Contractor with bending schedules showing the location, types sizes, bending dimensions and cut lengths of the reinforcement required to be fixed in the Works.

The Contractor shall check each bending schedule against the relevant drawing and shall notify the Engineer that the bending schedule is correct, or inform him of any discrepancies.  In particular the Contractor may be required to modify the schedules with respect to any reinforcement starting bars he may consider necessary after obtaining the Engineer’s approval.

9.03 Reinforcement shall be cut and bent to the shapes and dimensions shown on the
finally agreed bending schedules.  All reinforcement shall be carefully bent to the correct dimension in a manner, which will not injure the material.  In particular, no reinforcement shall be heated before bending.  Unless stated otherwise in the schedules, all bends and bending shall be in accordance with B.S. 4466.

Where laps are required in reinforcement bars they should be staggered so that only 1 bar in 5 is lapped at a particular section.  The Engineer based on the requirements of BSCP, 114, will determine the length of lap.  Reinforcement shall not be welded.

9.04 All reinforcement shall be rigidly fixed in position to the spacing, cover or other
dimensions indicated on the Drawings.  To prevent displacement before and during concreting the bars shall be bound together at all inter-sections with soft iron wire and the ends of the wire shall be turned inwards away from the surface of the structure, or with steel wire clips acceptable to the Engineer.

All reinforcement shall be perfectly clean and free from loose scale, rust, oil, grease and other matter, which might reduce the bond between the steel and the concrete.  Loose pieces of bending wire, timber and other foreign matter shall be removed.

9.05 Spacer blocks shall be provided to ensure that the reinforcement is correctly 
positioned in the Works and shall be as small as possible consistent with their purpose.  Such blocks shall not exceed 50 mm in length and their thickness shall be exactly that required to give cover specified on the Drawings.  Each spacer block shall be made of concrete class 37.5/10 and binding wire shall be securely embedded into each block to permit adequate fastening to the reinforcement bars.


10 PRECAST CONCRETE

10.01 Precast concrete covers all precast units for use in the Works, whether 
instructed under the Contract or proposed by the Contractor.

10.02 Formwork and reinforcement for precast concrete shall comply with the 
Specifications for insitu concrete.



10.03 Concrete for precast units shall comply with the Specifications for insitu concrete using the class of concrete specified in the drawings.

10.04 Requirements for curing shall be generally as for insitu concrete.  The Contractor shall ensure that units do not suffer any loss of moisture or sudden changes of temperature for at least four days after casting.  If a water spray is used for curing, the water shall be at a temperature within 50C of the temperature of the unit being cured.

10.05 Units shall be accurately formed to the dimensions shown in the Drawings 
and within the tolerances set out in B.S.C.P. 110


10.06  The formed faces of precast units shall be finished to class F3.  Free faces shall be finished to class UF2 unless another class of finish is specified on the Drawings.


10.07Precast units shall be handled and stored in a manner which will not cause
damage of any kind and shall be stored on a hard impermeable base.


10.08 Precast units shall be capable of safely sustaining the loads which they have 
Been designed to carry.  The Contractor shall subject units selected by the Engineer to load tests simulating the working conditions.  Details of such tests shall be agreed between the Engineer and the Contractor.

11.  MISCELLANEOUS STRUCTURES

11.01 Where concrete surfaces are required to be rendered in the finished works, the concrete surface shall be scared or hacked to provide a key for the render.


11.02 The formwork for all suspended slabs and beams shall be constructed with an 
Upward camber as follows:

Roof slabs and beams having two or more supports:  
6mm at mid-span for each 3m of clear span.

Other slabs and beams having two or more supports:
3mm at mid-span for each 3m of clear span.

Cantilever slabs and beams:
6mm at the unsupported end for each 3m projection 

11.03 The Contractor shall incorporate in concrete members all electrical conduit 
pipes fixing blocks, chases, boles, etc required by any sub-contractor. The Contractor shall obtain from the sub-contractor full details of his requirements and shall submit details to the Engineers for approval before work is put in hand.  All fixing blocks, chases, holes, etc. shall be accurately set out and cast into the concrete.  Neither holes nor chases shall be out in the hardened concrete without the prior approval of the Engineer.

11.04 Before reinforcement is placed, the internal faces of the formwork may be 
coated with an approved preparation to prevent adhesion of the concrete to the forms.  The preparation shall not be allowed to touch the reinforcement. 

Immediately before placing concretes all extraneous materials shall be removed from the interior of the formwork.  Each section of the formwork shall be inspected immediately before concreting commences.

12 BLOCKWORK

12.01 Block work Materials 

Cement:  Cement shall be as specified in “Concrete Works”

Sand:  Sand for mortar shall be as specified under fine Aggregates for concrete works

Water:  Water shall be as specified under works.

12.02 Cement mortar shall be composed or one part of cement to four parts of sand
(1.4) Mortar may be mixed by hand or mechanically.  Hand mixed shall be carried out on a clean watertight platform.  The ingredients shall be mixed thoroughly in the required proportions, first dry and then with the addition of water until a uniform consistency is obtained. The mortar should be used within one hour of the addition of the mixing water and any mortar not used shall be discarded.

12.03  The whole of the blocks required shall be in an approved machine to provide 
by the Contractor and shall have a minimum crushing strength of 2.5N/Sq.mm of gross area at 28 days.  The blocks shall be composed of 1.6 cement and sand measured by volume unless other wise specified or directed on the site, turned three times dry until an even colour and consistency throughout.  Water shall then be added gently from watering can through a hose, the quantity of water added being just sufficient to secure adhesion.  After wetting the mixture shall be turned over three times and well rammed into moulds and smoothed off with steel faced tool.  After removal from the machine on pallets, the blocks shall be matured under shade in separate rows one block high with a space between each block, and for at least 24 hours.  They shall then be removed from the pallets, but shall not be stacked up or removed from shade for at least a further seven days, then stacked not more than 5 blocks high in shade for a minimum of 14 days and kept well-watered all the time.

Alternatively blocks may be obtained from an approved supplier.  Blocks so obtained shall conform in all respects to above specifications.

No blocks shall be built into any part of the building until they have been matured for at least fourteen days.  The faces of blocks except where otherwise described shall be left rough for plastering or rendering.


The foundation blocks shall be 450mm by 225mm deep and shall be solid.  All shall be cast true to shape, even in size, square and free from flaws or holes with clean and sharp arises and equal to a sample approved by the Engineer.  All blocks shall be carefully handled.  Blocks with broken arises shall not be used.


12.04 Block Laying:  The block work shall be carried up in a uniform manner.  No 
one portion shall be raised more than 900mm above another at any time.  The work shall be carried up course by course and the height of four courses when laid shall be 900mm.

All pretends and quoins shall be kept strictly true and square and all work properly bonded together and carefully leveled through every second course.  All corners cross wall junctions and reveals shall be properly bonded.  Special care shall be taken that all vertical joints are filled with mortar.

All internal faces and external faces shall have raked out joints for plaster unless otherwise specified.

All block work finished fair faced shall have true and even face and all vertical and horizontal mortar joints shall be finished flush with the face of the block work.

All blocks shall be well wetted before being laid or built on.

Any defective blocks found in the work shall be cut out and replaced by sound ones at the Contractor’s expense.

12.05 Where required, walls shall be plastered externally with 19 mm thick cement 
and sand (1.4) plaster to an even but rough finish.  When rough fixture in plaster is required it shall be roughcast plaster sprayed on internal walls and underside of flat slabs shall be rendered with sand-cement plaster to a smooth but level finish with 
12mm thick cement-sand plaster.

13. ROOFING

13.01 Aluminum Sheet Roofing 

(i) Aluminum sheet Roofing shall be 22 or 24 (S.W.G) corrugated aluminum sheets depending upon the spacing of the purlins and laid all as hereinafter described for corrugated sheet iron roofing except that side laps shall be not less than two and a half corrugations.

(ii) Hips, ridges and valleys shall be formed with 20 or 22 (S.W.G.) flat aluminum sheeting, machine bent, and fixed all as hereafter described for sheet iron hips, ridges and valleys
  
All aluminum in contact with concrete with concrete or masonry shall be given on coat bituminous paint before fixing.

13.02 Galvanized Corrugated Iron Roofing

(i) Corrugated iron roofing shall be 24 (S.W.G.) galvanized corrugated iron sheets in accordance with B.S. 3083 and obtained from an approved manufacturer.  Sheets shall be of the sizes indicated on the drawings and laid with side laps of not less than one and a half corrugations.  Side laps shall be turned from the prevailing wind.  End laps shall be not less than 150mm.  Sheets shall be fixed to metal purlins with 8mm galvanized hook bolts, washers and nuts and to wood purlins with 62mm galvanized drive screws with an approved composition washer.  Screws shall be fixed through the ridges of the corrugation on each purlin.  Holes for screws shall be punched from the underside to the outside of the sheets.

(iii) Hips, ridges and valleys to corrugated iron roofs shall be formed 
with lengths of 24 (S.W.G.) flat galvanized iron sheet 375mm wide shaped as required to fit the profile of ridges, hips and valleys and in lengths not less than = 80m sheets shall be lapped 100 mm at the junctions of hips, ridges, passing, etc, and fixed with the same screws and washers as these holding the upper ends of the roofing sheets on both sides.

13.03 The whole of the roof coverings shall be left clean, sound, wind and water-tight 
on completion to the satisfaction of the Engineer.

13.04 Fixing Details for Sheeting

14.STRUCTURAL TIMBER

14.01 (i)  Structural Timber 

All structural timber shall comply with the requirements of B.S. 5268 Part 2.

     (ii) Stability
The Contractor is responsible for ensuring the stability of the works at all stages during construction.

       (iii) Timber
Structural timber shall be well seasoned Timber free from all defects and complying with the current B.S. 112.  The Contractor shall visually grade the timber using suitably qualified staff.

    In addition the limits of warping as defined in B.S. 656 shall be:

(a) Cup – on cup is allowed on faces of 100mm or less, cut on faces greater than 100mm shall not be more than 2mm/100mm

(b) Spring – maximum bow allowed shall be 5 mm per 3 linear metre.

© Bow – maximum bow allowed shall be 5mm per 3 linear metre

(d) Twist – 3 degrees per 3 linear metre

(iv) Workmanship
       Nails
       Nails shall be made from steel and comply with B.S. 12.2 Part 1 Table 2 and be 
       galvanized to B.S. 2989

(v) Joist Hanger
   Joist Hanger shall be made from 1 mm mild steel plate and galvanized to B.S. 2989
After punching of nail holes.


(vi) Assembly of Structural Units
Full size templates shall be used wherever possible to achieve uniformity and accuracy in setting out of structural elements.

(vii) Tolerances 
Tolerances for fabrication, assembly and erection shall be such that the dimensions achieved shall comply with B.S. 5606, Table 3.

(viii) Storage on and off Site

All timber components shall be stored so that they are protected against exposure to the weather, wetting, damage decay and insect attack.

(ix) Transport and Lifting

All materials and assemblies shall be protected from the weather and suitable measures should be taken to protect the surfaces during hoisting, transporting and erection.

Over stressing of members during handling and transportation shall be avoided by the provision of adequate support and the use of approved lifting methods.

15  PAINTING AND DECORATION

15.01 All paints, including priming; undercoats and finishing shall be obtained from approved manufactures.

15.02 All paints shall be used exactly as received from manufacturers and according to their directions.  In no circumstances will the addition of thinners, dryers or other materials be permitted without the written consent of the Engineer.

All oil shall be of the best linseed.

Turpentine shall be of the best quality and the use of substitutes will not be permitted.

White lead for stopping, etc, shall be of the best quality delivered on the site in maker’s containers/

15.03 All materials shall b e supplied strictly in accordance with the manufacturer’s instructions.  The work must be executed in the best manner and each coat is carried round the building before the next coat is applied.  The work must be thoroughly prepared and cleaned down before the priming of first coat of paint is applied and between each coat.

Before any part of the painting is commenced and Contractor is to be careful remove all dust and dirt from the surrounding part of the premises and shall take all necessary steps to minimize nuisance from dust during painting operations.

Cutting-in shall be nearly and accurately performed.

The contents of the cans shall be thoroughly stirred prior to pouring into kettles.

On completion of the works all floors are to be twice washed.  All marks on paints are to be sponged off, the work generally to be touched up after all other workmen have left and the whole of the works left clean and perfect on completion, to the satisfaction of the Engineer.

15.04 All surfaces to be painted shall be prepared as follows:

(a) Block and Concrete
All blocks and concrete surfaces shall be rendered and plasterwork shall be carefully cut out, stopped and made good and plasterwork shall be rubbed smooth.

(b)Iron and Steel

Iron and steelwork, whether delivered primed or unprimed shall be thoroughly scrapped, wire brushed or otherwise cleaned down to remove all rust and loose scale and primed on site before or after fixing, as directed.  All open joints shall be stopped with red or white lead putty.

© Woodwork 
The knots in all woodwork shall be knotted with shellac but black and projecting knots shall be cut out and the holes filled in with hard stopping, of dry white lead and gold size.  The woodwork shall be well pumiced down and brought to be a smooth surface

Priming of woodwork before delivery shall not be carried out until after the Engineer’s inspection.  Priming paint should comply with B.S. 2521.

All hidden portions of woodwork, including backs of door frames, shall be primed before the work is fixed and all glazing rebates shall be primed before glazing and front putties before painting.

15.05:  All work shall be rubbed down between each coat and stopped or faced up as necessary

15.06All coats of paint shall be thoroughly dry before the application of another coat.

15.07 Each coat shall be of different tint.

16 FENCING

16.01 Where shown in the Drawing or directed the Engineer the Contractor shall provide and erect fences, including excavation and backfilling, which fencing shall comply with the details shown in the drawings.

All timber for fencing shall be well-seasoned straight-grained hardwood to the approval of the Engineer.  After all cutting and drilling has been completed the timber shall be impregnated by the vacuum/pressure process with a copper/chrome composition preservative approved by the Engineer in accordance with BS.4072 to achieve an anticipated average dry salt retention of 12 kg/m3.  Prior to delivery of materials to the site samples shall be submitted by the Contractor to the Engineer for testing to ensure that the correct treatment has been applied.

Galvanizing of fencing wire shall be in accordance with BS 443.
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SKETCH OF PROJECT SIGN POST 

1000 mm

                                                                              
600mm
FUND:     DACF-RFG              
 FUNDING AGENT: ELLEMBELLE DISTRICT ASSEMBLY    
GOVERNMENT OF GHANA
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PROJECT: CONSTRUCTION OF 1NO.MATERNITY BLOCK AND 1NO.LABORATORY AND RADIOLOGY BLOCK NKROFUL

CLIENT:        ELLEMBELLE DISTRICT ASSEMBLY
		     
CONTRACTOR:

		          …………………….……………………………………..
ELLEMBELLE DISTRICT ASSEMBLY
P. O. BOX 34
NKROFUL
CONSULTANT:  WORKS DEPARTMENT, 
                             ELLEMBELLE DISTRICT ASSEMBY
                              P. O. BOX 34, NKROFUL
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Annex A Form:  Tender Security (Bank Guarantee)


Whereas, [name of Tenderer] (hereinafter called “the Tenderer”) has submitted his Tender dated [date] for the construction of [name of Contract] (hereinafter called “the Tender”).

Know all people by these presents that We [name of Bank] of [name of country] having our registered office at [address] (hereinafter called “the Bank”) are bound unto name of Employer] (hereinafter called “the Employer”) in the sum of [amount][footnoteRef:11] for which payment well and truly to be made to the said Employer, the Bank binds itself, its successors, and assigns by these presents. [11:  The Tenderer should insert the amount of the Guarantee in words and figures denominated in the currency of the Employer’s country or an equivalent amount in a freely convertible currency.  This figure should be the same as shown in Clause 16.1 of the Instructions to Tenderers.] 


Sealed with the Common Seal of the said Bank this [day] day of [month], [year].

The conditions of this obligation are:

(1)	If, after Tender opening, the Tenderer withdraws his Tender during the period of Tender validity specified in the Form of Tender; or

(2)	If the Tenderer having been notified of the acceptance of his Tender by the Employer during the period of Tender validity:

(a)	fails or refuses to execute the Form of Agreement in accordance with the Instructions to Tenderers, if required; or

(b)	fails or refuses to furnish the Performance Security, in accordance with the Instruction to Tenderers; or

(c)	does not accept the correction of the Tender Price pursuant to Clause 27,

we undertake to pay to the Employer up to the above amount upon receipt of his first written demand, without the Employer’s having to substantiate his demand, provided that in his demand the Employer will note that the amount claimed by him is due to him owing to the occurrence of one or any of the three conditions, specifying the occurred condition or conditions.


This Guarantee will remain in force up to and including the date [number] days[footnoteRef:12] after the deadline for submission of Tenders as such deadline is stated in the Instructions to Tenderers  or as it may be extended by the Employer, notice of which extension(s) to the Bank is hereby waived. Any demand in respect of this Guarantee should reach the Bank not later than the above date. [12:  Usually 28 days after the end of the validity period of the Tender.  The date should be inserted by the Employer before the Tender documents are issued.] 




Date 		Signature of the Bank 	

Witness 		Seal 	


	
[signature, name, and address]
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Annex B Form (Alternative 1):  Performance Bank Guarantee (Unconditional)


To:  [name and address of Employer]

Whereas [name and address of Contractor] (hereinafter called “the Contractor”) has undertaken, in pursuance of Contract No. [number] dated [date] to execute [name of Contract and brief description of Works] (hereinafter called “the Contract”);

And whereas it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognized bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

And whereas we have agreed to give the Contractor such a Bank Guarantee;

Now therefore we hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of [amount of Guarantee] [amount in words],[footnoteRef:13] such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of [amount of Guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein. [13:  An amount is to be inserted by the Guarantor, representing the percentage of the Contract Price specified in the Contract, and denominated either in the currency (ies) of the Contract or in a freely convertible currency acceptable to the Employer.] 


We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall be valid until a date 28 days from the date of issue of the Certificate of Completion.



Signature and seal of the Guarantor 	

Name of Bank 	
Address 	
Date 	
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Annex B Form (Alternative 2):  Performance Bond

By this Bond, [name and address of Contractor] as Principal (hereinafter called “the Contractor”) and [name, legal title, and address of surety, bonding company, or insurance company] as Surety (hereinafter called “the Surety”), are held and firmly bound unto [name and address of Employer] as Obligee (hereinafter called “the Employer”) in the amount of [amount of Bond] [amount of Bond in words],[footnoteRef:14] for the payment of which sum well and truly to be made in the types and proportions of currencies in which the Contract Price is payable, the Contractor and the Surety bind themselves, their heirs, executors, administrators, successors, and assigns, jointly and severally, firmly by these presents. [14:  An amount is to be inserted by the Surety, representing the percentage of the Contract Price specified in the Contract Data, and denominated either in the currency(ies) of the Contract or in a freely convertible currency of type and amount acceptable to the Employer.] 


Whereas the Contractor has entered into a Contract with the Employer dated[footnoteRef:15] the [day] day of [month], [year] for [name of Contract] in accordance with the documents, plans, specifications, and amendments thereto, which to the extent herein provided for, are by reference made part hereof and are hereinafter referred to as the Contract. [15:  Date of Letter of Acceptance or Agreement.] 


Now, therefore, the Condition of this Obligation is such that, if the Contractor shall promptly and faithfully perform the said Contract (including any amendments thereto), then this obligation shall be null and void; otherwise it shall remain in full force and effect.  Whenever the Contractor shall be, and declared by the Employer to be, in default under the Contract, the Employer having performed the Employer’s obligations thereunder, the Surety may promptly remedy the default, or shall promptly:

(1)	complete the Contract in accordance with its terms and conditions; or

(2)	obtain a Tender or Tenders from qualified Tenderers for submission to the Employer for completing the Contract in accordance with its terms and conditions, and upon determination by the Employer and the Surety of the lowest responsive Tenderer, arrange for a Contract between such Tenderer and Employer and make available as work progresses (even though there should be a default or a succession of defaults under the Contract or Contracts of completion arranged under this paragraph) sufficient funds to pay the cost of completion less the balance of the Contract Price; but not exceeding, including other costs and damages for which the Surety may be liable hereunder, the amount set forth in the first paragraph hereof.  The term “Balance of the Contract Price,” as used in this paragraph, shall mean the total amount payable by the Employer to the Contractor under the Contract, less the amount properly paid by the Employer to the Contractor; or

(3)	pay the Employer the amount required by the Employer to complete the Contract in accordance with its terms and conditions up to a total not exceeding the amount of this Bond.

The Surety shall not be liable for a greater sum than the specified penalty of this Bond.

Any suit under this Bond must be instituted before the expiration of one year from the date of issuance of the Certificate of Completion.

No right of action shall accrue on this Bond to or for the use of any person or corporation other than the Employer named herein or the heirs, executors, administrators, successors, and assigns of the Employer.

In testimony whereof, the Contractor has hereunto set its hand and affixed its seal, and the Surety has caused these presents to be sealed with its corporate seal duly attested by the signature of its legal representative, this [day] day of [month], [year].



Signed by 	
on behalf of [name of Surety] in the capacity of 	
In the presence of 	
Date 	



Signed by 	
on behalf of [name of Contractor] in the capacity of 	
In the presence of 	
Date 	
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Annex C Form: Bank Guarantee for Advance Payment

To:	[name and address of Employer]

	[name of Contract]

Gentlemen:

In accordance with the provisions of the Conditions of Contract, Clause 51 (“Advance Payment”) of the above-mentioned Contract, [name and address of Contractor] (hereinafter called “the Contractor”) shall deposit with [name of Employer] a Bank Guarantee to guarantee his proper and faithful performance under the said Clause of the Contract in an amount of [amount of Guarantee] [amount in words].[footnoteRef:16]  [16:  An amount is to be inserted by the Bank representing the amount of the Advance Payment, and denominated either in the currency(ies) of the Advance Payment as specified in the Contract, or in a freely convertible currency acceptable to the Employer.] 


We, the [Bank], as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligator and not as Surety merely, the payment to [name of Employer] on his first demand without whatsoever right of objection on our part and without his first claim to the Contractor, in the amount not exceeding [amount of Guarantee] [amount in words].[footnoteRef:17] [17:  An amount is to be inserted by the Bank representing the amount of the Advance Payment, and denominated either in the currency(ies) of the Advance Payment as specified in the Contract, or in a freely convertible currency acceptable to the Employer.] 


We further agree that no change or addition to or other modification of the terms of the Contract or of Works to be performed thereunder or of any of the Contract documents which may be made between [name of Employer] and the Contractor, shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall remain valid and in full effect from the date of the advance payment under the Contract until [name of Employer] receives full repayment of the same amount from the Contractor.

Yours truly,

Signature and seal:  	

Name of Bank:  	
Address:  	
Date:  	
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